## Instructions
ISMS BC/DR Assessment - RPO/RTO Compliance Matrix
Document ID: | ISMS-IMP-A.5.30.S3
Assessment: | RPO/RTO Compliance Matrix
Version: | 1.0
Generated: | 08.02.2026 11:48
PURPOSE
This workbook aligns Business Impact Analysis (BIA) requirements with technical BC/DR capabilities to identify gaps.
Use this to ensure technical capabilities meet business requirements for RPO (Recovery Point Objective) and RTO (Recovery Time Objective).
KEY PRINCIPLE: Requirements come from business (BIA), capabilities come from testing (not assumptions).
ASSESSMENT WORKFLOW
1. Populate System_Inventory from BIA results (business RPO/RTO requirements)
2. Populate Capability_Assessment with TESTED technical capabilities
3. Review Compliance_Matrix (formulas automatically compare requirements vs capabilities)
4. Document identified gaps in Gap_Analysis with remediation plans
5. Collect evidence in Evidence_Register (MINIMUM 5 evidence items for audit)
6. Review Summary dashboard for overall compliance metrics
7. Complete Approval_Sign_Off workflow (3 levels: Assessor → ISO → CISO)
8. Re-assess quarterly to track improvement
WORKSHEET DESCRIPTIONS
Instructions: | This sheet - comprehensive usage guide
Summary: | Executive dashboard with compliance metrics and gap summary
System_Inventory: | BIA results - business requirements (RPO/RTO from business impact)
Capability_Assessment: | Technical capabilities - TESTED recovery times (not assumptions)
Compliance_Matrix: | Automated comparison - requirement vs capability for each system
Gap_Analysis: | Identified gaps with risk scoring and remediation tracking
Evidence_Register: | 100 evidence slots for audit traceability (minimum 5 required)
Approval_Sign_Off: | 3-level approval workflow (Assessor → ISO → CISO)
DATA ENTRY GUIDELINES
TIME FORMAT: All times in HOURS (e.g., 0.25 = 15 min, 0.5 = 30 min, 1 = 1 hour, 24 = 1 day, 168 = 1 week)
SYSTEM_INVENTORY: Data from Business Impact Analysis (BIA) - business requirements
CAPABILITY_ASSESSMENT: Data from TESTING - actual measured recovery times (restore tests, failover tests)
CRITICAL: Capabilities must be TESTED, not assumed - untested = "Unknown"
COMPLIANCE: Use dropdown lists where provided for consistent data entry
RPO COMPLIANCE: System is RPO compliant if Backup Frequency ≤ RPO Requirement
RTO COMPLIANCE: System is RTO compliant if Recovery Capability ≤ RTO Requirement
OVERALL COMPLIANCE: Both RPO AND RTO must be compliant for overall compliance
AUTOMATIC FORMULA LOGIC
RPO Capability = Backup Frequency (how often you backup determines your RPO)
RTO Capability = MIN(Restore Time, Failover Time) - whichever is faster
RPO Compliance = f"{CHECK} Compliant" if RPO Capability ≤ RPO Requirement, else f"{XMARK} Non-Compliant"
RTO Compliance = f"{CHECK} Compliant" if RTO Capability ≤ RTO Requirement, else f"{XMARK} Non-Compliant"
Overall Compliance = f"{CHECK} Full Compliance" if both RPO & RTO compliant
Priority = "🔴 Critical" if Tier 1 system AND non-compliant (requires immediate attention)
Risk Score = Criticality Weight × Gap Severity (high score = high risk)
EVIDENCE COLLECTION REQUIREMENTS
✅ MINIMUM 5 EVIDENCE ITEMS REQUIRED for audit compliance
• Business Impact Analysis (BIA) report (RPO/RTO requirements source)
• Backup test results (actual restore time measurements)
• Failover test results (actual failover time measurements)
• Gap analysis and remediation plans
• Compliance calculations and summary reports
• System inventory and criticality documentation
• Testing schedules and historical test logs
STATUS INDICATOR LEGEND
✅ | Compliant / Success / Yes / Verified / Closed
❌ | Non-Compliant / Failure / No / Not Verified / Open
⚠ | Partial Compliance / Warning
⏳ | In Progress / Pending
❓ | Unknown / Not Tested
➖ | Not Applicable / Risk Accepted
🔴 | Critical Priority (immediate attention required)
🟡 | High Priority
🟢 | Medium Priority
⚪ | Low Priority
CRITICAL AUDIT REQUIREMENTS
❗ EVIDENCE: Minimum 5 evidence items required in Evidence_Register
❗ APPROVAL: All 3 sign-off levels required (Assessor, ISO, CISO)
❗ TESTING: Capabilities must be TESTED (restore tests, failover tests)
❗ CRITICAL SYSTEMS: Tier 1 systems must meet RPO/RTO requirements
❗ GAP REMEDIATION: All 🔴 Critical priority gaps require remediation plans
❗ QUARTERLY REVIEW: Re-assess every 90 days to maintain compliance

## Summary
RPO/RTO COMPLIANCE DASHBOARD
Assessment Date: 08.02.2026 ¦ Assessment ID: ISMS-IMP-A.5.30.S3
OVERALL RPO/RTO COMPLIANCE
Total Systems Assessed:
Systems with Full Compliance (RPO & RTO):
Systems with Partial Compliance:
Non-Compliant Systems:
Unknown Status (Not Tested):
Overall Compliance Rate:
COMPLIANCE BY CRITICALITY TIER
Tier 1 - Critical Systems:
Tier 1 - Full Compliance:
Tier 1 - Compliance Rate:
Tier 2 - Important Systems:
Tier 2 - Full Compliance:
Tier 2 - Compliance Rate:
GAP ANALYSIS SUMMARY
Total Gaps Identified:
🔴 Critical Priority Gaps:
🟡 High Priority Gaps:
🟢 Medium Priority Gaps:
⚪ Low Priority Gaps:
Open Gaps (🔴):
In Progress Gaps (⏳):
Closed Gaps (✅):
Average Risk Score:
EVIDENCE & APPROVAL STATUS
Evidence Items Collected:
Verified Evidence:
Minimum Evidence Required: | 5
Evidence Compliance:
Assessment Status:
Level 1 - Assessor Completed:
Level 2 - ISO Review:
Level 3 - CISO Approval:
PRIORITY ACTIONS
1. Address all 🔴 Critical priority gaps immediately (target: 90 days)
2. Test all systems marked ❓ Unknown (capability assessment needed)
3. Focus on Tier 1 systems first (business-critical)
4. Close RPO gaps: Increase backup frequency OR implement replication
5. Close RTO gaps: Implement redundancy OR optimize restore procedures
6. Collect minimum 5 evidence items in Evidence_Register
7. Complete all 3 approval levels (Assessor → ISO → CISO)
8. Track remediation progress in Gap_Analysis worksheet
9. Reassess quarterly to measure continuous improvement

## System_Inventory
SYSTEM INVENTORY - BIA RESULTS (Business Requirements)
Source: Business Impact Analysis (BIA) - RPO/RTO requirements from business stakeholders
System Name | Business Process | Criticality Tier | MTPD (hours) | RPO Requirement (hours) | RTO Requirement (hours) | Business Justification
E-Commerce Website | Online Sales | Tier 1 - Critical | 4 | 1 | 2 | Revenue loss $5K/hour, customer exodus after 4 hours downtime
Payment Gateway | Payment Processing | Tier 1 - Critical | 1 | 0.25 | 0.5 | Revenue loss immediate, regulatory compliance (PCI-DSS), reputation damage
Email System | Communication | Tier 1 - Critical | 8 | 4 | 4 | Business communication essential, brief outage tolerable, regulatory notifications
CRM System | Customer Management | Tier 1 - Critical | 12 | 2 | 6 | Sales operations halt, customer service degraded, revenue impact
ERP System | Finance, HR, Procurement | Tier 2 - Important | 24 | 4 | 12 | Can operate manually for 24 hours, critical for month-end close
HR Information System | HR Operations | Tier 2 - Important | 48 | 24 | 24 | Payroll at risk beyond 2 days, can work around short-term
File Server | Document Storage | Tier 3 - Standard | 168 | 24 | 48 | Inconvenience only, users have local copies, non-critical operations
Document Repository | Knowledge Management | Tier 3 - Standard | 168 | 168 | 72 | Non-critical reference system, acceptable long recovery time
Test Database | Development Testing | Tier 4 - Low | 720 | 168 | 168 | Can rebuild from production, low business impact, dev environment only
Training System | Employee Training | Tier 4 - Low | 720 | 720 | 168 | Training can be postponed, minimal business impact, non-essential
DATA SOURCE: Business Impact Analysis (BIA) - Requirements are business-driven, not IT-driven
MTPD = Maximum Tolerable Period of Disruption ¦ RPO = Recovery Point Objective ¦ RTO = Recovery Time Objective

## Capability_Assessment
CAPABILITY ASSESSMENT (Technical Capabilities - TESTED)
Source: Testing Results - Actual measured recovery times (restore tests, failover tests)
System Name | Backup Frequency (hours) | Restore Time Tested (hours) | Failover Time Tested (hours) | RPO Capability (hours) | RTO Capability (hours) | Test Notes / Observations
E-Commerce Website | 1 | 4 | 0.5 |  |  | Hourly backups, Active-Passive cluster, tested failover 30 min
Payment Gateway | 0.25 |  | 0.08 |  |  | 15-min transaction log backups, Active-Active cluster, failover ~5 min
Email System | 4 | 12 |  |  |  | Every 4 hours backup via cloud, no redundancy, restore tested at 12 hours
CRM System | 2 | 8 |  |  |  | Every 2 hours incremental backup, restore tested at 8 hours, no failover
ERP System | 24 | 8 |  |  |  | Daily full backup, restore tested at 8 hours, cold standby available
HR Information System | 24 | 20 |  |  |  | Daily backup, complex dependencies, restore tested at 20 hours
File Server | 168 | 24 |  |  |  | Weekly backup to tape, restore tested at ~24 hours, low priority
Document Repository | 168 | 48 |  |  |  | Weekly backup, large data volume, restore takes ~2 days
Test Database | 168 | 4 |  |  |  | Weekly backup, small DB, fast restore, can rebuild from production
Training System | 720 | 168 |  |  |  | Monthly backup, rarely tested, long restore time acceptable
DATA SOURCE: Testing Results - CRITICAL: Capabilities must be TESTED, not assumed. Untested = Unknown compliance.
RPO Capability = Backup Frequency ¦ RTO Capability = MIN(Restore Time, Failover Time) - formulas auto-calculate

## Compliance_Matrix
RPO/RTO COMPLIANCE MATRIX (Requirement vs Capability)
Automatic comparison: Business Requirements (System_Inventory) vs Technical Capabilities (Capability_Assessment)
System Name | Criticality | RPO: Req vs Cap | RTO: Req vs Cap | Overall Compliance | Priority | Gap Summary | Next Action Required
Monitor continuously, maintain current state
Monitor continuously, critical system
Consider more frequent backups (currently 4hr, need 4hr RTO)
Implement hot standby for faster recovery
Acceptable compliance, monitor quarterly
Acceptable compliance, monitor quarterly
Acceptable for Tier 3, no action required
Acceptable for Tier 3, no action required
Acceptable for Tier 4, no action required
Acceptable for Tier 4, no action required
COMPLIANCE SUMMARY METRICS
Total Systems:
Full Compliance (✅):
Partial Compliance (⚠️):
Non-Compliant (❌):
Unknown (❓):
Overall Compliance Rate:

## Gap_Analysis
GAP ANALYSIS & REMEDIATION TRACKING
Document identified gaps with risk scoring and remediation plans
Gap ID | System | Gap Type | Gap Description | Risk Score (1-10) | Priority | Remediation Plan | Status
GAP-001 |  | E-Commerce Website | RTO Gap | RTO requirement 2hr, current capability 4hr (restore time), missing redundancy | 8 | 🟡 High | Implement Active-Passive cluster to achieve <2hr RTO via failover | ⏳ In Progress
GAP-002 |  | Payment Gateway | Testing Gap | Failover capability exists but not tested in last 90 days, compliance unknown | 9 | 🔴 Critical | Schedule failover test within 30 days, document results | 🔴 Open
GAP-003 |  | CRM System | RTO Gap | RTO requirement 6hr, current restore time 8hr, no failover capability | 7 | 🟡 High | Optimize restore procedures, implement parallel restore, target <6hr | ⏳ In Progress
GAP-004 |  | Email System | RTO Gap | RTO requirement 4hr, restore time 12hr, no redundancy | 6 | 🟡 High | Consider cloud email with built-in redundancy (Office 365, Gmail) | 🔴 Open
GAP-005 |  | HR Information System | Both RPO & RTO | RPO req 24hr, backup frequency 24hr (at limit), RTO req 24hr, restore time 20hr | 5 | 🟢 Medium | Monitor closely, acceptable but no margin for error | ➖ Risk Accepted
GAP-006 |  | File Server | RPO Gap | RPO requirement 24hr, backup frequency 168hr (weekly) | 4 | 🟢 Medium | Increase backup frequency to daily (24hr) to meet RPO requirement | ✅ Closed
GAP-007 |  | Document Repository | Testing Gap | Restore time not tested, compliance status unknown | 3 | 🟢 Medium | Schedule restore test, document actual restore time | ⏳ In Progress
GAP-008 |  | Test Database | Documentation Gap | BIA not performed, RPO/RTO requirements undefined | 2 | ⚪ Low | Conduct BIA for dev/test systems, document acceptable recovery times | 🔴 Open
GAP-009 |  | Payment Gateway | RPO Gap | RPO requirement 15min, backup frequency 15min (at limit, no margin) | 8 | 🔴 Critical | Implement continuous replication (synchronous) to eliminate RPO gap | ⏳ In Progress
GAP-010 |  | Training System | Both RPO & RTO | Requirements far exceed capabilities but Tier 4 (low priority), risk acceptable | 1 | ⚪ Low | No action required, business accepts risk for non-critical system | ➖ Risk Accepted
GAP-011
GAP-012
GAP-013
GAP-014
GAP-015
GAP-016
GAP-017
GAP-018
GAP-019
GAP-020
GAP-021
GAP-022
GAP-023
GAP-024
GAP-025
GAP-026
GAP-027
GAP-028
GAP-029
GAP-030
GAP-031
GAP-032
GAP-033
GAP-034
GAP-035
GAP-036
GAP-037
GAP-038
GAP-039
GAP-040
GAP-041
GAP-042
GAP-043
GAP-044
GAP-045
GAP-046
GAP-047
GAP-048
GAP-049
GAP-050
GAP-051
GAP-052
GAP-053
GAP-054
GAP-055
GAP-056
GAP-057
GAP-058
GAP-059
GAP-060
GAP-061
GAP-062
GAP-063
GAP-064
GAP-065
GAP-066
GAP-067
GAP-068
GAP-069
GAP-070
GAP-071
GAP-072
GAP-073
GAP-074
GAP-075
GAP-076
GAP-077
GAP-078
GAP-079
GAP-080
GAP-081
GAP-082
GAP-083
GAP-084
GAP-085
GAP-086
GAP-087
GAP-088
GAP-089
GAP-090
GAP-091
GAP-092
GAP-093
GAP-094
GAP-095
GAP-096
GAP-097
GAP-098
GAP-099
GAP-100
GAP-101
GAP-102
GAP-103
GAP-104
GAP-105
GAP-106
GAP-107
GAP-108
GAP-109
GAP-110
GAP SUMMARY METRICS
Total Gaps Identified:
🔴 Critical Priority:
🟡 High Priority:
🟢 Medium Priority:
⚪ Low Priority:
🔴 Open Gaps:
⏳ In Progress:
✅ Closed Gaps:
➖ Risk Accepted:
Average Risk Score:
Max Risk Score:

## Evidence_Register
EVIDENCE REGISTER
Document all evidence supporting this assessment (MINIMUM 5 evidence items required for audit compliance)
Evidence ID | Evidence Type | Description | Related Sheet/Row | Location/Path | Date Collected | Collected By | Verification Status
EVD-001 |  | BIA Report | Business Impact Analysis Q1 2024 - RPO/RTO requirements | System_Inventory (all rows) | /evidence/bia/BIA_Report_Q1_2024.pdf | 08.02.2026 | BC/DR Coordinator | ✅ Verified
EVD-002 |  | Test Result | E-Commerce restore test results - 4hr restore time | Capability_Assessment!A5 | /evidence/testing/ecommerce_restore_test_2024-01-05.pdf | 03.02.2026 | Infrastructure Team | ✅ Verified
EVD-003 |  | Test Result | Payment Gateway failover test - 5min failover time | Capability_Assessment!A6 | /evidence/testing/payment_failover_test_2024-01-03.pdf | 01.02.2026 | Infrastructure Team | ✅ Verified
EVD-004 |  | Screenshot | Backup monitoring dashboard - all systems backup status | Backup_Inventory (WB1) | /evidence/monitoring/backup_dashboard_2024-01-10.png | 08.02.2026 | Backup Administrator | ✅ Verified
EVD-005 |  | Config File | Backup schedule configuration - all systems | System_Inventory | /evidence/configs/backup_schedules.json | 06.02.2026 | Backup Administrator | ✅ Verified
EVD-006 |  | Report | RPO/RTO compliance calculations - automated report | Compliance_Matrix | /evidence/reports/rpo_rto_compliance_2024-01-10.xlsx | 08.02.2026 | Assessment Team | ⏳ Pending
EVD-007 |  | Diagram | High-availability architecture diagram - critical systems | Capability_Assessment (Tier 1) | /evidence/diagrams/ha_architecture_2024.vsdx | 29.01.2026 | Solutions Architect | ✅ Verified
EVD-008 |  | Policy Document | BC/DR Policy - RPO/RTO requirements policy | All worksheets | /evidence/policies/ISMS-POL-A813-814-530.pdf | 09.01.2026 | ISO Coordinator | ✅ Verified
EVD-009
EVD-010
EVD-011
EVD-012
EVD-013
EVD-014
EVD-015
EVD-016
EVD-017
EVD-018
EVD-019
EVD-020
EVD-021
EVD-022
EVD-023
EVD-024
EVD-025
EVD-026
EVD-027
EVD-028
EVD-029
EVD-030
EVD-031
EVD-032
EVD-033
EVD-034
EVD-035
EVD-036
EVD-037
EVD-038
EVD-039
EVD-040
EVD-041
EVD-042
EVD-043
EVD-044
EVD-045
EVD-046
EVD-047
EVD-048
EVD-049
EVD-050
EVD-051
EVD-052
EVD-053
EVD-054
EVD-055
EVD-056
EVD-057
EVD-058
EVD-059
EVD-060
EVD-061
EVD-062
EVD-063
EVD-064
EVD-065
EVD-066
EVD-067
EVD-068
EVD-069
EVD-070
EVD-071
EVD-072
EVD-073
EVD-074
EVD-075
EVD-076
EVD-077
EVD-078
EVD-079
EVD-080
EVD-081
EVD-082
EVD-083
EVD-084
EVD-085
EVD-086
EVD-087
EVD-088
EVD-089
EVD-090
EVD-091
EVD-092
EVD-093
EVD-094
EVD-095
EVD-096
EVD-097
EVD-098
EVD-099
EVD-100
EVIDENCE COLLECTION SUMMARY
Total Evidence Items:
✅ Verified Evidence:
⏳ Pending Verification:
❌ Not Verified:
Minimum Required: | 5
Compliance Status:

## Approval_Sign_Off
ASSESSMENT APPROVAL & SIGN-OFF
ASSESSMENT SUMMARY
Assessment Document: | RPO/RTO Compliance Matrix
Assessment ID: | ISMS-IMP-A.5.30.S3
ISO 27001:2022 Controls: | A.5.30 (Information Backup)
Assessment Period: | [USER INPUT - e.g., Q1 2024, January 2024]
Total Systems Assessed:
Overall RPO/RTO Compliance Rate:
Critical Priority Gaps:
Open Gaps Requiring Remediation:
Critical Gaps Summary: | [USER INPUT - list critical gaps from Gap_Analysis]
Evidence Items Collected:
Assessment Status: | [SELECT FROM DROPDOWN]
LEVEL 1: ASSESSMENT COMPLETED BY
Name:
Role/Title:
Department:
Email:
Date Completed:
Signature/Initials:
LEVEL 2: REVIEWED BY (INFORMATION SECURITY OFFICER)
Name:
Review Date:
Review Notes:
Recommendation:
LEVEL 3: APPROVED BY (CISO / SECURITY DIRECTOR)
Name:
Approval Date:
Approval Decision:
Conditions/Notes:
NEXT REVIEW DETAILS
Next Review Date (Quarterly):
Review Responsible:
Special Considerations:
APPROVAL WORKFLOW REQUIREMENTS
• All 3 approval levels must be completed for final approval
• Minimum 5 evidence items must be documented in Evidence_Register
• Assessment status must be "Final" before CISO approval
• If "Requires Remediation", re-assessment required after gap closure
• Quarterly re-assessment recommended for continuous compliance (RPO/RTO capabilities change)
• Critical priority gaps (🔴) require executive awareness and remediation tracking