## Instructions & Legend
ISMS-IMP-A.8.25-26-29.S4 ISO/IEC 27001:2022 - Controls A.8.25, A.8.26, A.8.29: Secure Development
ISO/IEC 27001:2022 - Control A.8.29: Security Testing in Development and Acceptance
Document ID: | ISMS-IMP-A.8.25-26-29.S4
Assessment Area: | Vulnerability Remediation Tracking
Related Policy: | ISMS-POL-A.8.25-26-29-S4
Version: | 1.0
Assessment Date: | [USER INPUT]
Completed By: | [USER INPUT]
Organization: | [USER INPUT]
Review Cycle: | Monthly
How to Use This Workbook
1. Maintain current vulnerability inventory in Open_Vulnerabilities_Inventory
2. Monitor SLA compliance in Remediation_SLA_Compliance
3. Track vulnerability trends over time in Vulnerability_Trends
4. Document accepted security risks in Security_Technical_Debt
5. Review Compliance_Summary for overall remediation performance
6. Document evidence in Evidence_Register
7. Obtain monthly approvals in Approval_Sign_Off
Remediation SLA Reference
Severity | SLA | Description
Critical | 7 days | Immediate exploitation, high impact
High | 30 days | Likely exploitation, significant impact
Medium | 90 days | Exploitation requires conditions, moderate impact
Low | Best effort | Difficult to exploit or minimal impact

## Open_Vulnerabilities_Inventory
Open Vulnerabilities Inventory
Track all open security vulnerabilities with SLA monitoring
Vulnerability ID | Application Name | Vulnerability Type | Severity | Source | Discovered Date | Age (days) | SLA Due Date | Days Until Due | Status | Owner | Notes
VULN-2025-001 | Customer Portal | SQL Injection | High | SAST | 2024-12-15 |  |  |  | In Progress | Dev Team A | In payment module
VULN-2025-002 | Customer Portal | XSS | Medium | DAST | 2024-12-20 |  |  |  | Open | Dev Team A | User profile page
VULN-2025-003 | Internal HR | Outdated Dependency | High | SCA | 2024-12-10 |  |  |  | In Progress | Dev Team B | Log4j 2.14.0
VULN-2025-004 | Marketing Site | Missing Security Headers | Low | DAST | 2025-01-05 |  |  |  | Open | Dev Team C | X-Frame-Options
VULN-2025-005 | API Gateway | Authentication Bypass | Critical | Pentest | 2025-01-08 |  |  |  | In Progress | Security Team | OAuth implementation
Formulas:
Age (days) = TODAY()-[Discovered Date]
Days Until Due = IF([SLA Due Date]="N/A","N/A",[SLA Due Date]-TODAY())

## Remediation_SLA_Compliance
Remediation SLA Compliance
Monitor vulnerability remediation SLA compliance by severity
Severity Level | SLA (days) | Open Vulnerabilities | Vulnerabilities Within SLA | Vulnerabilities Overdue | Avg Age (days) | SLA Compliance Rate (%)
Critical | 7
High | 30
Medium | 90
Low | Best effort |  | N/A | N/A |  | N/A

## Vulnerability_Trends
Vulnerability Trends Over Time
Track vulnerability discovery and remediation trends month-over-month
Month | Critical Opened | Critical Closed | High Opened | High Closed | Medium Opened | Medium Closed | Low Opened | Low Closed | Total Opened | Total Closed | Net Change
2024-08 | 0 | 0 | 3 | 2 | 8 | 6 | 12 | 10
2024-09 | 0 | 0 | 2 | 3 | 10 | 8 | 15 | 12
2024-10 | 1 | 1 | 4 | 3 | 6 | 8 | 10 | 11
2024-11 | 0 | 0 | 3 | 4 | 9 | 7 | 14 | 13
2024-12 | 0 | 0 | 5 | 3 | 12 | 10 | 18 | 15
2025-01 | 1 | 0 | 4 | 2 | 8 | 5 | 11 | 8

## Security_Technical_Debt
Security Technical Debt (Accepted Risks)
Track vulnerabilities accepted as risk with mitigating controls
Vulnerability ID | Application Name | Vulnerability Type | Severity | Risk Acceptance Rationale | Accepted Date | Accepted By | Mitigating Controls | Review Date | Status
VULN-2024-087 | Legacy App | Outdated Framework | Medium | Decommissioning in 6 months | 2024-09-15 | CISO | WAF rules block known exploits | 2025-03-15 | Active
VULN-2024-102 | Internal Tool | Missing Security Headers | Low | Internal-only application | 2024-11-10 | Security Architect | Network segmentation | 2025-05-10 | Active

## Compliance_Summary
Vulnerability Remediation Compliance Dashboard
Overall vulnerability remediation performance and compliance
Portfolio Vulnerability Statistics
Total Open Vulnerabilities: | [Calculated from data]
Critical Vulnerabilities: | [Calculated from data]
High Vulnerabilities: | [Calculated from data]
Overdue Vulnerabilities: | [Calculated from data]
Average Remediation Time: | [Calculated from data]
Overall SLA Compliance Rate: | [Calculated from data]
Accepted Security Risks: | [Calculated from data]
SLA Compliance by Severity
Severity | SLA (days) | Open Count | Overdue Count | Compliance Rate (%) | Compliance Status
Critical
High
Medium
Low |  |  |  |  | N/A

## Evidence_Register
Evidence Register
Centralized register of vulnerability remediation evidence
Evidence Type | Vulnerability ID | Document Title/Description | Document Location/Link | Last Updated | Owner | Status
Remediation Ticket | VULN-2025-001 | Jira Ticket PROJ-1234 | https://jira.example.com/browse/PROJ-1234 | 2025-01-10 | Dev Team A | Current
Fix Validation | VULN-2025-003 | Re-scan Report (Snyk) | /reports/vuln/VULN-2025-003-retest.pdf | 2025-01-09 | Security Team | Current
Risk Acceptance | VULN-2024-087 | Risk Acceptance Form | /risk-acceptance/VULN-2024-087.pdf | 2024-09-15 | CISO | Current

## Approval_Sign_Off
Monthly Assessment Approval and Sign-Off
Assessment Information
Assessment Date: | [USER INPUT]
Assessed By: | [USER INPUT]
Organization: | [USER INPUT]
Assessment Month: | [USER INPUT - e.g., January 2025]
Total Open Vulnerabilities: | [Auto-calculated or USER INPUT]
Approval Sign-Off
Approver Name | Role/Title | Date | Signature | Comments
[Name] | Security Team Lead | [Date] | [Signature/Initials]
[Name] | Development Manager | [Date] | [Signature/Initials]
[Name] | CISO / Security Leadership | [Date] | [Signature/Initials]
Overall Remediation Compliance
SLA Compliance Status: | [✅ Compliant / ⚠️ At Risk / ❌ Non-Compliant]
Overall SLA Compliance Rate: | [X%]