## Instructions
ISMS BC/DR Assessment - BC/DR Testing Results Tracker
Document ID: | ISMS-IMP-A.8.13.4
Assessment: | BC/DR Testing Results
Version: | 1.0
Generated: | 31.01.2026 03:18
PURPOSE
This workbook tracks all BC/DR testing activities, results, issues discovered, and testing compliance.
Use this to demonstrate that backup, failover, and DR capabilities are regularly TESTED, not just assumed.
KEY PRINCIPLE: "Test or it doesn't work" - Untested recovery capability = no recovery capability.
TESTING WORKFLOW
1. Plan tests in Test_Schedule (define annual test plan)
2. Execute tests according to schedule
3. Log results in Test_Results_Log (document actual test execution)
4. Document issues in Issue_Remediation (problems discovered during testing)
5. Track remediation of issues to closure
6. Review Testing_Compliance (annual compliance assessment)
7. Collect evidence in Evidence_Register (MINIMUM 5 evidence items for audit)
8. Review Summary dashboard for overall testing compliance
9. Complete Approval_Sign_Off workflow (3 levels: Assessor → ISO → CISO)
10. Repeat annually for continuous compliance
TEST TYPES EXPLAINED
Backup Restore: | Test restoring data from backup - verify RPO capability (A.8.13)
Failover Test: | Test switching to redundant system - verify RTO capability (A.8.14)
Full DR Scenario: | End-to-end disaster recovery test - complete system recovery (A.5.30)
Tabletop Exercise: | Discussion-based walkthrough of DR procedures (no actual execution)
Component Test: | Test individual component (e.g., database restore only)
Integration Test: | Test multiple components together (e.g., app + database recovery)
WORKSHEET DESCRIPTIONS
Instructions: | This sheet - comprehensive usage guide
Summary: | Executive dashboard with testing compliance metrics
Test_Schedule: | Annual test plan - what tests to perform when (110 rows)
Test_Results_Log: | All test executions - actual test results (110 rows)
Issue_Remediation: | Issues discovered during testing - track to closure (110 rows)
Testing_Compliance: | Annual compliance assessment - are we testing enough? (110 rows)
Evidence_Register: | 100 evidence slots for audit traceability (minimum 5 required)
Approval_Sign_Off: | 3-level approval workflow (Assessor → ISO → CISO)
TESTING FREQUENCY GUIDELINES
TIER 1 - CRITICAL SYSTEMS:
• Backup Restore: Quarterly (every 3 months)
• Failover Test: Quarterly (every 3 months)
• Full DR Scenario: Annual (at least once per year)
TIER 2 - IMPORTANT SYSTEMS:
• Backup Restore: Semi-Annual (every 6 months)
• Failover Test: Semi-Annual (every 6 months)
• Full DR Scenario: Annual (at least once per year)
TIER 3 - STANDARD SYSTEMS:
• Backup Restore: Annual (at least once per year)
• Failover Test: Annual (if redundancy exists)
TIER 4 - LOW SYSTEMS:
• Testing may be ad-hoc or not required (risk acceptance)
STATUS INDICATOR LEGEND
✅ | Success / Compliant / Closed / Verified
❌ | Failure / Non-Compliant / Open
⚠ | Partial Success / Overdue / Warning
⏳ | In Progress / Pending
❓ | Unknown / Not Tested
➖ | Not Started / Risk Accepted / Not Applicable
🔄 | Cancelled / Rescheduled
🔴 | Critical Severity / Open Issue
🟡 | High Severity
🟢 | Medium Severity
⚪ | Low Severity
CRITICAL TESTING REQUIREMENTS
❗ CRITICAL SYSTEMS: Tier 1 systems MUST be tested quarterly (backup & failover)
❗ EVIDENCE: Minimum 5 evidence items required (test reports, logs, screenshots)
❗ ISSUES: All 🔴 Critical issues must have remediation plans
❗ APPROVAL: All 3 sign-off levels required (Assessor, ISO, CISO)
❗ ANNUAL DR: Full DR scenario test required at least once per year
❗ DOCUMENTATION: All tests must be documented with results (success/failure)

## Summary
BC/DR TESTING COMPLIANCE DASHBOARD
Assessment Date: 31.01.2026 ¦ Assessment ID: ISMS-IMP-A.8.13.4
TESTING ACTIVITY SUMMARY
Total Tests Scheduled:
Tests Completed (✅ Success):
Tests Partial Success (⚠️):
Tests Failed (❌):
Tests In Progress (⏳):
Tests Not Started (➖):
Test Success Rate:
TESTING COMPLIANCE BY CRITICALITY
Tier 1 - Critical Systems:
Tier 1 - Compliant:
Tier 1 - Compliance Rate:
Tier 2 - Important Systems:
Tier 2 - Compliant:
Tier 2 - Compliance Rate:
ISSUE SUMMARY
Total Issues Identified:
🔴 Critical Issues:
🟡 High Severity Issues:
🟢 Medium Severity Issues:
⚪ Low Severity Issues:
Open Issues (🔴):
In Progress (⏳):
Closed Issues (✅):
EVIDENCE & APPROVAL STATUS
Evidence Items Collected:
Verified Evidence:
Minimum Evidence Required: | 5
Evidence Compliance:
Assessment Status:
Level 1 - Assessor Completed:
Level 2 - ISO Review:
Level 3 - CISO Approval:
PRIORITY ACTIONS
1. Address all 🔴 Critical issues discovered during testing
2. Complete all overdue tests (⚠️ Overdue in Testing_Compliance)
3. Schedule quarterly tests for Tier 1 systems
4. Remediate test failures (❌ Failed tests in Test_Results_Log)
5. Document lessons learned from partial successes (⚠️)
6. Collect minimum 5 evidence items in Evidence_Register
7. Complete all 3 approval levels (Assessor → ISO → CISO)
8. Plan next annual full DR scenario test
9. Update runbooks based on test findings

## Test_Schedule
BC/DR TEST SCHEDULE (Annual Plan)
Define annual test plan - what tests to perform when (schedule all required tests)
Test ID | System Name | Test Type | Criticality | Required Frequency | Scheduled Date | Test Owner | Notes / Prerequisites
TEST-001 |  | E-Commerce Website | Backup Restore | Tier 1 - Critical | Quarterly | 15.02.2026 | Infrastructure Team | Restore full website DB, verify data integrity, test 4hr restore time
TEST-002 |  | E-Commerce Website | Failover Test | Tier 1 - Critical | Quarterly | 17.03.2026 | Infrastructure Team | Test Active-Passive cluster failover, verify <30min RTO
TEST-003 |  | Payment Gateway | Failover Test | Tier 1 - Critical | Quarterly | 02.03.2026 | Payments Team | Test Active-Active failover, critical system, must coordinate with processor
TEST-004 |  | Email System | Backup Restore | Tier 1 - Critical | Quarterly | 01.04.2026 | IT Operations | Restore mailbox data, test 12hr restore time, verify user access
TEST-005 |  | CRM System | Backup Restore | Tier 1 - Critical | Quarterly | 16.04.2026 | App Support Team | Restore CRM DB, verify integrations work, test 8hr restore time
TEST-006 |  | ERP System | Backup Restore | Tier 2 - Important | Semi-Annual | 01.05.2026 | ERP Team | Restore ERP DB, complex dependencies, test 8hr restore, schedule during low activity
TEST-007 |  | HR Information System | Backup Restore | Tier 2 - Important | Semi-Annual | 31.05.2026 | HR IT Team | Restore HR DB, sensitive data, coordinate with CISO, test 20hr restore
TEST-008 |  | All Critical Systems | Full DR Scenario | Tier 1 - Critical | Annual | 30.07.2026 | BC/DR Coordinator | Full DR exercise - simulate datacenter loss, recover all Tier 1 systems
TEST-009 |  | File Server | Backup Restore | Tier 3 - Standard | Annual | 29.08.2026 | IT Operations | Restore file share, test 24hr restore time, low priority
TEST-010 |  | BC/DR Team | Tabletop Exercise | Tier 1 - Critical | Annual | 02.03.2026 | BC/DR Coordinator | Walkthrough DR procedures with stakeholders, no actual execution
TEST-011
TEST-012
TEST-013
TEST-014
TEST-015
TEST-016
TEST-017
TEST-018
TEST-019
TEST-020
TEST-021
TEST-022
TEST-023
TEST-024
TEST-025
TEST-026
TEST-027
TEST-028
TEST-029
TEST-030
TEST-031
TEST-032
TEST-033
TEST-034
TEST-035
TEST-036
TEST-037
TEST-038
TEST-039
TEST-040
TEST-041
TEST-042
TEST-043
TEST-044
TEST-045
TEST-046
TEST-047
TEST-048
TEST-049
TEST-050
TEST-051
TEST-052
TEST-053
TEST-054
TEST-055
TEST-056
TEST-057
TEST-058
TEST-059
TEST-060
TEST-061
TEST-062
TEST-063
TEST-064
TEST-065
TEST-066
TEST-067
TEST-068
TEST-069
TEST-070
TEST-071
TEST-072
TEST-073
TEST-074
TEST-075
TEST-076
TEST-077
TEST-078
TEST-079
TEST-080
TEST-081
TEST-082
TEST-083
TEST-084
TEST-085
TEST-086
TEST-087
TEST-088
TEST-089
TEST-090
TEST-091
TEST-092
TEST-093
TEST-094
TEST-095
TEST-096
TEST-097
TEST-098
TEST-099
TEST-100
TEST-101
TEST-102
TEST-103
TEST-104
TEST-105
TEST-106
TEST-107
TEST-108
TEST-109
TEST-110
TEST SCHEDULE SUMMARY
Total Tests Scheduled:
Backup Restore Tests:
Failover Tests:
Full DR Scenarios:
Tier 1 System Tests:
Quarterly Tests:

## Test_Results_Log
BC/DR TEST RESULTS LOG (Execution History)
Document all test executions - actual test results (log every test performed)
Result ID | Test ID (Schedule) | System Name | Test Type | Test Date | Result | Actual Duration (hrs) | Tested By | Issues Found | Detailed Notes
RES-001 |  | TEST-001 | E-Commerce Website | Backup Restore | 26.01.2026 | ✅ Success | 3.8 | Infrastructure Team | None | Full restore successful, verified data integrity, 3.8hr restore time
RES-002 |  | TEST-002 | E-Commerce Website | Failover Test | 16.01.2026 | ⚠ Partial Success | 0.6 | Infrastructure Team | ISS-002, ISS-003 | Failover worked but took 36min (exceeds 30min RTO), found monitoring gaps
RES-003 |  | TEST-003 | Payment Gateway | Failover Test | 11.01.2026 | ✅ Success | 0.08 | Payments Team | None | Failover successful, ~5min, no transaction loss, excellent result
RES-004 |  | TEST-004 | Email System | Backup Restore | 01.01.2026 | ❌ Failure | 16 | IT Operations | ISS-001 | Restore failed, backup corrupted, root cause: backup job misconfiguration
RES-005 |  | TEST-005 | CRM System | Backup Restore | 17.12.2025 | ⚠ Partial Success | 9.5 | App Support Team | ISS-004 | Restore successful but took 9.5hr (exceeds 8hr RTO), integration issues post-restore
RES-006 |  | TEST-006 | ERP System | Backup Restore | 02.12.2025 | ✅ Success | 7.2 | ERP Team | None | Restore successful, complex dependencies resolved, 7.2hr within 8hr target
RES-007 |  | TEST-010 | BC/DR Team | Tabletop Exercise | 21.01.2026 | ✅ Success | 2 | BC/DR Coordinator | ISS-005 | Tabletop successful, identified gaps in communication procedures
RES-008 |  | TEST-008 | All Critical Systems | Full DR Scenario | 02.11.2025 | ⚠ Partial Success | 12 | BC/DR Coordinator | ISS-006, ISS-007, ISS-008 | DR scenario partially successful, 3/5 Tier 1 systems recovered within RTO
RES-009 |  | TEST-009 | File Server | Backup Restore | 03.10.2025 | ✅ Success | 22 | IT Operations | None | Restore successful, 22hr within 24hr target, Tier 3 system
RES-010 |  | TEST-007 | HR Information System | Backup Restore | 18.09.2025 | ✅ Success | 18.5 | HR IT Team | None | Restore successful, 18.5hr within 20hr target, sensitive data verified
RES-011
RES-012
RES-013
RES-014
RES-015
RES-016
RES-017
RES-018
RES-019
RES-020
RES-021
RES-022
RES-023
RES-024
RES-025
RES-026
RES-027
RES-028
RES-029
RES-030
RES-031
RES-032
RES-033
RES-034
RES-035
RES-036
RES-037
RES-038
RES-039
RES-040
RES-041
RES-042
RES-043
RES-044
RES-045
RES-046
RES-047
RES-048
RES-049
RES-050
RES-051
RES-052
RES-053
RES-054
RES-055
RES-056
RES-057
RES-058
RES-059
RES-060
RES-061
RES-062
RES-063
RES-064
RES-065
RES-066
RES-067
RES-068
RES-069
RES-070
RES-071
RES-072
RES-073
RES-074
RES-075
RES-076
RES-077
RES-078
RES-079
RES-080
RES-081
RES-082
RES-083
RES-084
RES-085
RES-086
RES-087
RES-088
RES-089
RES-090
RES-091
RES-092
RES-093
RES-094
RES-095
RES-096
RES-097
RES-098
RES-099
RES-100
RES-101
RES-102
RES-103
RES-104
RES-105
RES-106
RES-107
RES-108
RES-109
RES-110
TEST RESULTS SUMMARY
Total Tests Executed:
✅ Successful Tests:
⚠ Partial Success:
❌ Failed Tests:
Success Rate:
Average Test Duration (hrs):

## Issue_Remediation
ISSUE REMEDIATION TRACKER
Track issues discovered during testing to closure
Issue ID | Related Test (Result ID) | Issue Description | Root Cause | Severity | Status | Remediation Plan | Target Resolution Date
ISS-001 |  | RES-004 | Email system backup corrupted - restore failed | Backup job misconfigured, missing transaction log backups | 🔴 Critical | ✅ Closed | Reconfigured backup job, added transaction log backups, verified with successful test | 11.01.2026
ISS-002 |  | RES-002 | E-Commerce failover took 36min (exceeds 30min RTO) | Manual DNS update required, not automated | 🟡 High | ✅ Closed | Automated DNS failover, reduced to <30min, retested successfully | 21.01.2026
ISS-003 |  | RES-002 | Monitoring did not alert during failover | Monitoring not configured for cluster failover events | 🟢 Medium | ✅ Closed | Configured monitoring for failover events, tested alerts | 23.01.2026
ISS-004 |  | RES-005 | CRM restore took 9.5hr (exceeds 8hr RTO) | Integration dependencies not documented in restore procedure | 🟡 High | ⏳ In Progress | Update restore runbook with integration steps, optimize restore process | 02.03.2026
ISS-005 |  | RES-007 | Communication procedures gap identified in tabletop | No clear escalation path defined for DR coordinator | 🟡 High | ✅ Closed | Documented escalation procedures, updated BC/DR plan | 26.01.2026
ISS-006 |  | RES-008 | Payment Gateway not recovered during DR scenario | Active-Active failover requires manual processor notification | 🔴 Critical | ⏳ In Progress | Automate processor notification, create runbook, retest in next DR scenario | 01.04.2026
ISS-007 |  | RES-008 | CRM not recovered within RTO during DR scenario | Complex dependencies, restore order not documented | 🟡 High | ⏳ In Progress | Document system dependency tree, define restore order, update runbook | 17.03.2026
ISS-008 |  | RES-008 | Network connectivity issues during DR scenario | DR site network not pre-configured, manual setup required | 🟡 High | 🔴 Open | Pre-configure DR site network, automate VPN setup, document procedures | 01.05.2026
ISS-009 |  | [General] | Test documentation inconsistent across teams | No standard template for test documentation | 🟢 Medium | ✅ Closed | Created standard test report template, distributed to all teams | 16.01.2026
ISS-010 |  | [General] | Lack of training for restore procedures | Staff turnover, new team members not trained on DR procedures | 🟡 High | ⏳ In Progress | Schedule quarterly DR training, create training materials, track completion | 02.03.2026
ISS-011
ISS-012
ISS-013
ISS-014
ISS-015
ISS-016
ISS-017
ISS-018
ISS-019
ISS-020
ISS-021
ISS-022
ISS-023
ISS-024
ISS-025
ISS-026
ISS-027
ISS-028
ISS-029
ISS-030
ISS-031
ISS-032
ISS-033
ISS-034
ISS-035
ISS-036
ISS-037
ISS-038
ISS-039
ISS-040
ISS-041
ISS-042
ISS-043
ISS-044
ISS-045
ISS-046
ISS-047
ISS-048
ISS-049
ISS-050
ISS-051
ISS-052
ISS-053
ISS-054
ISS-055
ISS-056
ISS-057
ISS-058
ISS-059
ISS-060
ISS-061
ISS-062
ISS-063
ISS-064
ISS-065
ISS-066
ISS-067
ISS-068
ISS-069
ISS-070
ISS-071
ISS-072
ISS-073
ISS-074
ISS-075
ISS-076
ISS-077
ISS-078
ISS-079
ISS-080
ISS-081
ISS-082
ISS-083
ISS-084
ISS-085
ISS-086
ISS-087
ISS-088
ISS-089
ISS-090
ISS-091
ISS-092
ISS-093
ISS-094
ISS-095
ISS-096
ISS-097
ISS-098
ISS-099
ISS-100
ISS-101
ISS-102
ISS-103
ISS-104
ISS-105
ISS-106
ISS-107
ISS-108
ISS-109
ISS-110
ISSUE REMEDIATION SUMMARY
Total Issues:
🔴 Critical Issues:
🟡 High Severity:
🟢 Medium Severity:
🔴 Open Issues:
⏳ In Progress:
✅ Closed Issues:
Issue Closure Rate:

## Testing_Compliance
TESTING COMPLIANCE ASSESSMENT (Annual Review)
Annual compliance assessment - are systems being tested according to requirements?
System Name | Test Type | Criticality | Required Frequency | Last Test Date | Days Since Last Test | Compliance Status | Next Test Due
E-Commerce Website | Backup Restore | Tier 1 - Critical | Quarterly | 22.11.2025
E-Commerce Website | Failover Test | Tier 1 - Critical | Quarterly | 28.10.2025
Payment Gateway | Failover Test | Tier 1 - Critical | Quarterly | 02.12.2025
Email System | Backup Restore | Tier 1 - Critical | Quarterly | 03.10.2025
CRM System | Backup Restore | Tier 1 - Critical | Quarterly | 12.11.2025
ERP System | Backup Restore | Tier 2 - Important | Semi-Annual | 24.08.2025
HR Information System | Backup Restore | Tier 2 - Important | Semi-Annual | 25.07.2025
File Server | Backup Restore | Tier 3 - Standard | Annual | 06.04.2025
Document Repository | Backup Restore | Tier 3 - Standard | Annual | 16.01.2025
Test Database | Backup Restore | Tier 4 - Low | Ad-Hoc
TESTING COMPLIANCE SUMMARY
Total Systems Tracked:
✅ Compliant:
⚠ Overdue:
❌ Non-Compliant:
❓ Unknown (Never Tested):
Overall Compliance Rate:
Tests Overdue/Non-Compliant:
Formulas:
Days Since Last Test = IF([Last Test Date]="","",TODAY()-[Last Test Date])

## Evidence_Register
EVIDENCE REGISTER
Document all evidence supporting this assessment (MINIMUM 5 evidence items required for audit compliance)
Evidence ID | Evidence Type | Description | Related Sheet/Row | Location/Path | Date Collected | Collected By | Verification Status
EVD-001 |  | Test Report | E-Commerce backup restore test report - Q1 2024 | Test_Results_Log!A5 (RES-001) | /evidence/testing/ecommerce_restore_Q1_2024.pdf | 26.01.2026 | Infrastructure Team | ✅ Verified
EVD-002 |  | Test Report | Payment Gateway failover test report with timing data | Test_Results_Log!A7 (RES-003) | /evidence/testing/payment_failover_2024-01-03.pdf | 11.01.2026 | Payments Team | ✅ Verified
EVD-003 |  | Screenshot | Full DR scenario test dashboard - all system status | Test_Results_Log!A12 (RES-008) | /evidence/testing/dr_scenario_dashboard_2023-10-15.png | 02.11.2025 | BC/DR Coordinator | ✅ Verified
EVD-004 |  | Video Recording | Tabletop exercise recording - team walkthrough | Test_Results_Log!A11 (RES-007) | /evidence/testing/tabletop_exercise_2024-01-01.mp4 | 21.01.2026 | BC/DR Coordinator | ✅ Verified
EVD-005 |  | Log File | Email backup job failure logs - ISS-001 root cause | Issue_Remediation!A5 (ISS-001) | /evidence/logs/email_backup_failure_2023-12-10.log | 27.12.2025 | IT Operations | ✅ Verified
EVD-006 |  | Issue Ticket | Jira ticket ISS-006 - Payment Gateway DR scenario issue | Issue_Remediation!A10 (ISS-006) | /evidence/tickets/JIRA-BCDR-156.pdf | 07.11.2025 | BC/DR Coordinator | ✅ Verified
EVD-007 |  | Runbook | Updated E-Commerce restore runbook - post-test improvements | Test_Results_Log!A5 | /evidence/runbooks/ecommerce_restore_runbook_v2.2.pdf | 28.01.2026 | Infrastructure Team | ⏳ Pending
EVD-008 |  | Sign-Of | Annual DR test sign-off from CISO | Test_Results_Log!A12 | /evidence/approvals/annual_dr_test_signoff_2023.pdf | 02.11.2025 | CISO Office | ✅ Verified
EVD-009
EVD-010
EVD-011
EVD-012
EVD-013
EVD-014
EVD-015
EVD-016
EVD-017
EVD-018
EVD-019
EVD-020
EVD-021
EVD-022
EVD-023
EVD-024
EVD-025
EVD-026
EVD-027
EVD-028
EVD-029
EVD-030
EVD-031
EVD-032
EVD-033
EVD-034
EVD-035
EVD-036
EVD-037
EVD-038
EVD-039
EVD-040
EVD-041
EVD-042
EVD-043
EVD-044
EVD-045
EVD-046
EVD-047
EVD-048
EVD-049
EVD-050
EVD-051
EVD-052
EVD-053
EVD-054
EVD-055
EVD-056
EVD-057
EVD-058
EVD-059
EVD-060
EVD-061
EVD-062
EVD-063
EVD-064
EVD-065
EVD-066
EVD-067
EVD-068
EVD-069
EVD-070
EVD-071
EVD-072
EVD-073
EVD-074
EVD-075
EVD-076
EVD-077
EVD-078
EVD-079
EVD-080
EVD-081
EVD-082
EVD-083
EVD-084
EVD-085
EVD-086
EVD-087
EVD-088
EVD-089
EVD-090
EVD-091
EVD-092
EVD-093
EVD-094
EVD-095
EVD-096
EVD-097
EVD-098
EVD-099
EVD-100
EVIDENCE COLLECTION SUMMARY
Total Evidence Items:
✅ Verified Evidence:
⏳ Pending Verification:
❌ Not Verified:
Minimum Required: | 5
Compliance Status:

## Approval_Sign_Off
ASSESSMENT APPROVAL & SIGN-OFF
ASSESSMENT SUMMARY
Assessment Document: | BC/DR Testing Results Tracker
Assessment ID: | ISMS-IMP-A.8.13.4
ISO 27001:2022 Controls: | A.8.13 (Information Backup)
Assessment Period: | [USER INPUT - e.g., Annual 2024, Q1-Q4 2024]
Total Tests Executed:
Test Success Rate:
Critical Issues Open:
Testing Compliance Rate (Tier 1):
Critical Issues Summary: | [USER INPUT - list critical issues from Issue_Remediation]
Evidence Items Collected:
Assessment Status: | [SELECT FROM DROPDOWN]
LEVEL 1: ASSESSMENT COMPLETED BY
Name:
Role/Title:
Department:
Email:
Date Completed:
Signature/Initials:
LEVEL 2: REVIEWED BY (INFORMATION SECURITY OFFICER)
Name:
Review Date:
Review Notes:
Recommendation:
LEVEL 3: APPROVED BY (CISO / SECURITY DIRECTOR)
Name:
Approval Date:
Approval Decision:
Conditions/Notes:
NEXT REVIEW DETAILS
Next Annual Assessment:
Review Responsible:
Special Considerations:
APPROVAL WORKFLOW REQUIREMENTS
• All 3 approval levels must be completed for final approval
• Minimum 5 evidence items must be documented in Evidence_Register
• Assessment status must be "Final" before CISO approval
• All 🔴 Critical issues must have remediation plans
• Annual re-assessment required (next assessment due in 365 days)
• Quarterly testing required for Tier 1 systems (ongoing throughout year)