## Overview
Workbook ID | ISMS-IMP-A.8.8.8
Title | Vulnerability Remediation Tracking
Version | 1.0
Generated Date | 31.01.2026
Last Updated | [Manual entry]
Owner | Vulnerability Management Coordinator
Classification | Internal
Review Cycle | Weekly
QUICK STATISTICS
Metric | Formula/Source | Target
Total Active Remediations |  | -
P0 In Progress |  | <3
P1 In Progress |  | <50
Overdue Remediations |  | 0
SLA Compliance Rate |  | >95%
Patches Deployed This Week |  | -
Failed Deployments This Week |  | 0
Pending CAB Approvals |  | <10
Average Remediation Time |  | <14 days
Rollbacks This Month |  | 0
NAVIGATION LINKS
Remediation_Queue | Master remediation tracking (42 columns)
Deployment_Schedule | Maintenance windows and assignments
Change_Control | CAB approval workflow
Patch_Library | Available patches and compatibility
Testing_Validation | Pre-deployment testing results
Deployment_Log | Real-time deployment execution
Rollback_Procedures | Emergency rollback plans
SLA_Compliance | Detailed SLA tracking and escalations
Team_Assignments | Resource allocation and workload
Communication_Log | Stakeholder notifications
Lessons_Learned | Post-deployment reviews
Metrics_Dashboard | Executive KPIs and trends
Audit_Trail | Complete activity history

## Remediation_Queue
Vuln_ID | Discovery_Date | CVE_ID | Title | Affected_System | System_Type | Environment | Asset_Owner | Scanner_Source | CVSS_Version | CVSS_Primary_Score | CVSS_v40_Score | CVSS_v31_Score | CVSS_v40_Vector | CVSS_v31_Vector | Supplemental_AU | Supplemental_S | Version_Source | Score_Date | Final_Priority | SLA_Days | Due_Date | Days_Remaining | SLA_Status | Remediation_Type | Patch_ID | Patch_Version | Vendor_Advisory | Dependencies | Compatibility_Tested | Test_Environment | Change_Request_ID | Change_Type | CAB_Approval_Status | Approved_By | Approval_Date | Deployment_Window | Scheduled_Date | Deployed_By | Deployment_Status | Actual_Deployment_Date | Verification_Status
VULN-2026-001 | 2026-01-05 | CVE-2025-12345 | Remote Code Execution in Apache Struts | web-prod-01.example.com | Server | Production | Security Team | Nessus | v4.0 |  | 9.3 |  | CVSS:4.0/AV:N/AC:L/AT:N/PR:N/UI:N/VC:H/VI:H/VA:H/SC:N/SI:N/SA:N |  | Y | N | NVD | 2026-01-05 | P0 | 1 | 2026-01-06 |  |  | Patch | STRUTS-2025-001 | [5 empty] | CR-2026-EMG-001 | Emergency | Approved | CISO | 2026-01-05 | Emergency: Immediate |  |  | Complete | 2026-01-06 | Passed
VULN-2026-002 | 2026-01-08 | CVE-2025-67890 | SQL Injection in Web Application | app-db-01.dmz.local | Application | DMZ | Application Team | Qualys | v4.0 |  | 8.1 |  | CVSS:4.0/AV:N/AC:L/AT:N/PR:N/UI:N/VC:H/VI:L/VA:N/SC:N/SI:N/SA:N |  | N | N | NVD | 2026-01-08 | P1 | 7 | 2026-01-15 |  |  | Configuration Change | [6 empty] | CR-2026-0123 | Normal | Pending |  |  | MW1: Wed 22:00-02:00 | 2026-01-15 |  | Scheduled
VULN-2026-003 | 2026-01-10 | CVE-2025-11111 | Authentication Bypass in API | api-gateway.prod.local | Application | Production | Application Team | Manual Assessment | v4.0 |  | 7.5 |  | CVSS:4.0/AV:N/AC:L/AT:N/PR:L/UI:N/VC:H/VI:L/VA:N/SC:N/SI:N/SA:N |  | N | N | Vendor | 2026-01-10 | P2 | 30 | 2026-02-09 |  |  | Patch | API-2025-789 | [5 empty] | CR-2026-0145 | Normal | Approved |  | 2026-01-10 | MW2: Sat 20:00-06:00 |  |  | Rolled Back | 2026-01-11 | Failed
VULN-2026-004 | 2025-10-15 | CVE-2025-22222 | Cross-Site Scripting in Admin Panel | admin.dev.local | Application | Development | Application Team | OpenVAS | v3.1 |  |  | 5.4 |  | CVSS:3.1/AV:N/AC:L/PR:L/UI:R/S:C/C:L/I:L/A:N | N/A | N/A | Scanner | 2025-10-15 | P3 | 90 | 2026-01-13 |  |  | Patch | [12 empty] | 2026-01-20 |  | Scheduled
Formulas:
Days_Remaining = IF([Due_Date]<>"",NETWORKDAYS(TODAY(),[Due_Date]),"")
Note on K1: AUTO-CALCULATED: Uses v4.0 if available, else v3.1. Formula selects based on CVSS_Version (Column J).

## Deployment_Schedule
Window_ID | Window_Name | Schedule | Window_Date | Status | Total_Patches | P0_Count | P1_Count | P2_Count | Assigned_Team | Backup_Team | CAB_Approval | Rollback_Plan | Communication_Sent | Notes
MW1-2026-01-15 | MW1: Wednesday | Wed 22:00-02:00 | 2026-01-15 | Scheduled |  |  |  |  | Infrastructure Team | Security Team | Approved | Y | Y | Production infrastructure patches
MW2-2026-01-11 | MW2: Saturday | Sat 20:00-06:00 | 2026-01-11 | Complete | 50 | 0 | 5 | 20 | All Teams | N/A | Approved | Y | Y | Major deployment - completed successfully
EMG-2026-01-06 | Emergency | Immediate | 2026-01-06 | Complete | 1 | 1 | 0 | 0 | Security Team | Infrastructure Team | CISO Approved | Y | Y | P0 wormable vulnerability

## Change_Control
Change_Request_ID | Vuln_ID | Submission_Date | Requester | Change_Type | Approval_Status | CAB_Review_Date | Approved_By | Approval_Notes | Implementation_Date | Risk_Level | Impact_Assessment | Rollback_Required | Testing_Complete | Documentation_Attached | Status
CR-2026-0123 | VULN-2026-002 | 2026-01-08 | Security Engineer | Normal | Pending | 2026-01-13 |  |  | 2026-01-15 | Medium | Web application configuration change - minimal user impact | Y | Pending | Y | Submitted
CR-2026-EMG-001 | VULN-2026-001 | 2026-01-05 | Security Engineer | Emergency | Approved | 2026-01-05 | CISO | Emergency approval - wormable vulnerability | 2026-01-06 | Critical | Production servers - potential for exploitation | Y | Y | Y | Implemented

## Patch_Library
Patch_ID | Product | Current_Version | Patch_Version | Release_Date | Vendor | Patch_Type | CVE_IDs | KB_Article | Download_URL | File_Hash_SHA256 | File_Size_MB | Prerequisites | Known_Issues | Reboot_Required | Tested_In_Lab | Compatibility_Notes | Deployment_Count | Success_Rate
STRUTS-2025-001 | Apache Struts | 2.5.30 | 2.5.31 | 2026-01-05 | Apache Foundation | Security | CVE-2025-12345 | https://struts.apache.org/security | https://downloads.apache.org/struts/2.5.31 | a1b2c3... | 15.3 | Java 8+ | None | Y | Y | Compatible with all deployment methods
API-2025-789 | API Gateway | 3.2.1 | 3.2.2 | 2026-01-09 | Vendor X | Security | CVE-2025-11111 | https://vendor-x.com/kb-789 | https://downloads.vendor-x.com/api-3.2.2 | d4e5f6... | 42.1 | API Gateway 3.x | Known issue with load balancers | N | Y | Test with load balancer first | 0 | 0

## Testing_Validation
Test_ID | Vuln_ID | Patch_ID | Test_Environment | Test_Start_Date | Test_End_Date | Tester_Name | Test_Type | Test_Result | Functional_Test | Performance_Test | Security_Test | Regression_Test | Issues_Found | Resolution | Sign_Off_By | Sign_Off_Date | Proceed_To_Production | Notes
TEST-001 | VULN-2026-001 | STRUTS-2025-001 | Lab-Prod-Mirror | 2026-01-05 10:00 | 2026-01-05 14:00 | Security Engineer | Functional | Pass | ✅ Pass | ➖ N/A | ✅ Pass | ✅ Pass | None | N/A | Team Lead | 2026-01-05 | Y | Fast-tracked emergency testing

## Deployment_Log
Log_ID | Patch_ID | Vuln_ID | Deployment_Date | Deployment_Status | Affected_System | Deployed_By | Deployment_Method | Start_Time | End_Time | Duration_Minutes | Pre_Deployment_Backup | Pre_Deployment_Snapshot | Post_Deployment_Test | Service_Interruption | Downtime_Minutes | Error_Messages | Resolution_Actions | Rollback_Triggered | Final_Status | Verification_By | Notes
LOG-001 | STRUTS-2025-001 | VULN-2026-001 | 2026-01-06 00:30 | Success | web-prod-01.example.com | Security Engineer | Manual | 2026-01-06 00:30 | 2026-01-06 01:15 |  | ✅ Y | ✅ Y | ✅ Pass | N | 0 | None | N/A | N | Deployed | Team Lead | Emergency deployment - successful

## Rollback_Procedures
Rollback_ID | Vuln_ID | Patch_ID | Deployment_Log_ID | Rollback_Trigger | Triggered_By | Trigger_Date | Approval_Required | Approved_By | Rollback_Method | Rollback_Start | Rollback_End | Rollback_Status | Service_Restored | Data_Loss | Impact_Description | Root_Cause | Lessons_Learned | Remediation_Plan | Status

## SLA_Compliance
Vuln_ID | Final_Priority | SLA_Days | Discovery_Date | Due_Date | Days_Elapsed | Days_Remaining | SLA_Status | Current_Status | Blocker_Type | Blocker_Description | Escalation_Level | Last_Escalation_Date | Escalation_Notes | Extension_Requested | Extension_Approved | New_Due_Date | Approver

## Team_Assignments
Team_Name | Team_Lead | Total_FTE | Weekly_Hours | Assigned_P0 | Assigned_P1 | Assigned_P2 | Assigned_P3 | Total_Assigned | Estimated_Hours | Capacity_Used | Status | Availability_Notes
Security Team | Security Director | 4 | 160
Infrastructure Team | Infrastructure Lead | 12 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟢 Normal
Application Team | App Development Lead | 25 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 🟢 Normal

## Communication_Log
Communication_ID | Date_Sent | Communication_Type | Audience | Subject | Related_Vulns | Priority_Level | Message_Summary | Sent_By | Acknowledgment_Required | Acknowledgment_Received | Response_Deadline | Follow_Up_Required | Follow_Up_Date | Status

## Lessons_Learned
Review_ID | Review_Date | Vuln_ID | Deployment_Type | What_Went_Well | What_Went_Wrong | Root_Cause | Improvement_Actions | Action_Owner | Target_Date | Status | Impact_Category | Priority | Follow_Up_Notes

## Metrics_Dashboard
REMEDIATION PERFORMANCE METRICS
SECTION A: OVERALL PERFORMANCE
Metric | Formula | Target | Actual
Total Active Remediations |  | <500 | [Calculated]
SLA Compliance Rate |  | >95% | [Calculated]
Average Remediation Time |  | <14 days | [Calculated]
Deployment Success Rate |  | >98% | [Calculated]
Patches Deployed MTD |  | - | [Calculated]

## Audit_Trail
Timestamp | User | Action_Type | Record_Type | Record_ID | Field_Changed | Old_Value | New_Value | Change_Reason | IP_Address | Session_ID