## Executive Dashboard
ISMS-IMP-A.8.24.5 – Cryptography Compliance Summary Dashboard ISO/IEC 27001:2022 - Control A.8.24: Use of Cryptography - Executive Overview
Document Information
Document ID | ISMS-IMP-A.8.24.5
Report Type | Compliance Summary Dashboard
Related Policy | ISMS-POL-A.8.24 (Use of Cryptography)
Version | 1.0
Report Date
Reporting Period
Prepared By
Organization
Review Cycle | Quarterly
Last Updated | 46035
OVERALL CRYPTOGRAPHY COMPLIANCE STATUS
Metric | Score | Target | Status
Overall Compliance Rate | 66.775% | ≥95%
Critical Gaps | 0 | 0
High-Risk Items | 0 | ≤5
Remediation Progress | #DIV/0! | ≥80%
COMPLIANCE BY ASSESSMENT AREA
Assessment Area | Source Document | Overall Compliance % | Total Items | Compliant | Partial | Non-Compliant | Trend
Data Transmission | ISMS-IMP-A_8_24_1.xlsx | 45.3% | 106 | 48 | 10 | 6
Data Storage | ISMS-IMP-A_8_24_2.xlsx | 67.7% | 62 | 42 | 12 | 8
Authentication | ISMS-IMP-A_8_24_3.xlsx | 75% | 36 | 27 | 5 | 4
Key Management | ISMS-IMP-A_8_24_4.xlsx | 79.1% | 43 | 34 | 5 | 4
TOTAL | (Aggregated) | 66.775% | 247 | 151 | 32 | 22
KEY PERFORMANCE INDICATORS (KPIs)
KPI | Current Value | Target | Status | Last Quarter | Change
Cryptographic Controls Implemented |  | [Target]
Systems with Encryption at Rest |  | 100%
Systems with Encryption in Transit |  | 100%
MFA Coverage (All Users) |  | 100%
MFA Coverage (Admins) |  | 100%
Certificate Expiry Compliance |  | 100%
Key Rotation Compliance |  | ≥95%
Password Hashing Compliance |  | 100%
SSO Coverage |  | ≥80%
Open Critical Gaps | 0 | 0
TOP 5 CRITICAL SECURITY GAPS
Rank | Issue Description | Assessment Area | Risk Level | Systems Affected | Target Date | Owner | Status
1
2
3
4
5
EXECUTIVE SUMMARY
Assessment Period:
Overall Compliance Status: | #VALUE!
Security Posture: | #VALUE!
Key Achievements This Period:
Major Concerns:
Recommended Executive Actions:
1.
2.
3.
Budget Impact:
Total Estimated Remediation Budget: | 0
Approved Budget:
Budget Gap: | 0

## Gap Analysis
COMPREHENSIVE GAP ANALYSIS - CRYPTOGRAPHIC CONTROLS Consolidated view of all compliance gaps across assessment areas
Gap Summary Statistics
Assessment Area | Total Gaps | Critical | High | Medium | Low | Compliance % | Risk Score
Data Transmission | 22 | 0 | 0 | 0 | 0 |  | 0
Data Storage | 20 | 0 | 0 | 0 | 0 |  | 0
Authentication | 9 | 0 | 0 | 0 | 0 |  | 0
Key Management | 9 | 0 | 0 | 0 | 0 |  | 0
TOTAL | 60 | 0 | 0 | 0 | 0 | 0 | 0
DETAILED GAP REGISTER
Gap ID | Assessment Area | Source Document | System/Application | Gap Description | Policy Reference | Current State | Required State | Risk Level | Impact | Likelihood | Risk Score | Data Classification | Systems Affected | Users Impacted | Business Impact | Compensating Controls | Status | Exception ID | Risk ID
GAP-DAT-001 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | mail.company.com | Upgrade to TLS 1.3 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-002 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | legacy.company.com | URGENT: Decommission or upgrade | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-003 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | vpn.company.com | Plan TLS 1.3 upgrade | Partial | Compliant | Medium | Open | Yes
GAP-DAT-004 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | test.company.com | Use valid certificate | Partial | Compliant | Medium | Open | Yes
GAP-DAT-005 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | confluence.internal | Upgrade to TLS 1.3 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-006 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | jira.internal | Upgrade to TLS 1.3 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-007 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | backup.internal | Replace with valid cert | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-008 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Microsoft 365 | Increase S/MIME adoption to 95% | Partial | Compliant | Medium | Open | Yes
GAP-DAT-009 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Internal Mail Server | Promote PGP key usage | Partial | Compliant | Medium | Open | Yes
GAP-DAT-010 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Internal Approvals | Increase to 95% | Partial | Compliant | Medium | Open | Yes
GAP-DAT-011 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Email Signatures | Expand to all users | Partial | Compliant | Medium | Open | Yes
GAP-DAT-012 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Legacy FTP | URGENT: Migrate to SFTP | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-013 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Site-to-Site VPN (IPSec) | Add certificate auth + DH 20 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-014 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Contractor VPN (OpenVPN) | Upgrade: TLS 1.3 + MFA + AES-256 | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-015 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Network Devices | Migrate to key-based | Partial | Compliant | Medium | Open | Yes
GAP-DAT-016 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | IoT Devices | Implement key management | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-017 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Windows Workstations | Enforce MFA + TLS 1.3 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-018 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Legacy Systems | URGENT: Enable NLA + TLS 1.3 | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-019 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Legacy SOAP API | Upgrade TLS 1.3 + OAuth | Partial | Compliant | Medium | Open | Yes
GAP-DAT-020 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Oracle Database | Upgrade TLS 1.3 + AES-256 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-021 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | IoT WiFi | Migrate to WPA3 | Partial | Compliant | Medium | Open | Yes
GAP-DAT-022 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx | Warehouse WiFi | Upgrade WPA3 + 802.1X | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-001 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | BYOD iPhones (enrolled) | Increase enrollment | Partial | Compliant | Medium | Open | Yes
GAP-DAT-002 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | BYOD Android (enrolled) | Training needed | Partial | Compliant | Medium | Open | Yes
GAP-DAT-003 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Test Devices (50 units) | Enroll in MDM or decommission | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-004 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Legacy Tablets | Replace or decommission | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-005 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Linux Workstations (100 units) | Centralize key management | Partial | Compliant | Medium | Open | Yes
GAP-DAT-006 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Contractor Laptops (80 units) | Enforce encryption policy | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-007 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Legacy Desktops (50 units) | Upgrade or decommission | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-008 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Development Servers (50 units) | Automate key rotation | Partial | Compliant | Medium | Open | Yes
GAP-DAT-009 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Legacy Unix Servers (20 units) | Migrate or decommission | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-010 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | MongoDB Analytics (6 nodes) | Implement KMS rotation | Partial | Compliant | Medium | Open | Yes
GAP-DAT-011 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Redis Cache Cluster | Move keys to KMS | Partial | Compliant | Medium | Open | Yes
GAP-DAT-012 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Oracle Enterprise (4 nodes) | Upgrade to AES-256 + HSM | Partial | Compliant | Medium | Open | Yes
GAP-DAT-013 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Cassandra Cluster (8 nodes) | Automate key rotation | Partial | Compliant | Medium | Open | Yes
GAP-DAT-014 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | MariaDB Prod (6 nodes) | Implement KMS | Partial | Compliant | Medium | Open | Yes
GAP-DAT-015 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Test Databases | Implement encryption | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-016 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Personal Backup (Time Machine) | Enforce corporate backup | Partial | Compliant | Medium | Open | Yes
GAP-DAT-017 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Legacy Backup System | Migrate to encrypted solution | Non-Compliant | Compliant | High | Open | Yes
GAP-DAT-018 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Corporate SD Cards | Enforce hardware encryption | Partial | Compliant | Medium | Open | Yes
GAP-DAT-019 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | DVD/CD Media (archived) | Phase out optical media | Partial | Compliant | Medium | Open | Yes
GAP-DAT-020 | Data Storage | ISMS-IMP-A.8.24.2.xlsx | Standard USB Drives | Block standard USB via GPO | Non-Compliant | Compliant | High | Open | Yes
GAP-AUT-001 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Legacy Applications | Migrate or decommission | Non-Compliant | Compliant | High | Open | Yes
GAP-AUT-002 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Developer Systems | Enforce 100% MFA | Partial | Compliant | Medium | Open | Yes
GAP-AUT-003 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Legacy Systems | Implement MFA proxy | Non-Compliant | Compliant | High | Open | Yes
GAP-AUT-004 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Email Signing (S/MIME) | Increase to 100% | Partial | Compliant | Medium | Open | Yes
GAP-AUT-005 | Authentication | ISMS-IMP-A.8.24.3.xlsx | AD Group Managed Service Accounts | Migrate remaining services | Partial | Compliant | Medium | Open | Yes
GAP-AUT-006 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Database Service Accounts | Implement secret manager | Partial | Compliant | Medium | Open | Yes
GAP-AUT-007 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Legacy Service Accounts | Modernize authentication | Non-Compliant | Compliant | High | Open | Yes
GAP-AUT-008 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Custom Apps with SSO | Complete SSO integration | Partial | Compliant | Medium | Open | Yes
GAP-AUT-009 | Authentication | ISMS-IMP-A.8.24.3.xlsx | Legacy Apps (No SSO) | Implement SSO proxy | Non-Compliant | Compliant | High | Open | Yes
GAP-KEY-001 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Legacy DES Keys | Migrate to AES-256 | Non-Compliant | Compliant | High | Open | Yes
GAP-KEY-002 | Key Management | ISMS-IMP-A.8.24.4.xlsx | SSH Private Keys | Enforce passphrase policy | Partial | Compliant | Medium | Open | Yes
GAP-KEY-003 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Development Keys (local) | Implement Vault for dev | Non-Compliant | Compliant | High | Open | Yes
GAP-KEY-004 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Database Encryption Keys | Automate rotation | Partial | Compliant | Medium | Open | Yes
GAP-KEY-005 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Azure Storage Keys | Enable auto-rotation | Non-Compliant | Compliant | High | Open | Yes
GAP-KEY-006 | Key Management | ISMS-IMP-A.8.24.4.xlsx | SSH Host Keys | Implement rotation policy | Partial | Compliant | Medium | Open | Yes
GAP-KEY-007 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Personal SSH Keys | Centralized key management | Partial | Compliant | Medium | Open | Yes
GAP-KEY-008 | Key Management | ISMS-IMP-A.8.24.4.xlsx | S/MIME Certificates | Increase adoption to 100% | Partial | Compliant | Medium | Open | Yes
GAP-KEY-009 | Key Management | ISMS-IMP-A.8.24.4.xlsx | Legacy Self-Signed Certs | Replace with proper PKI | Non-Compliant | Compliant | High | Open | Yes
GAP-061
GAP-062
GAP-063
GAP-064
GAP-065
GAP-066
GAP-067
GAP-068
GAP-069
GAP-070
GAP-071
GAP-072
GAP-073
GAP-074
GAP-075
GAP-076
GAP-077
GAP-078
GAP-079
GAP-080
GAP-081
GAP-082
GAP-083
GAP-084
GAP-085
GAP-086
GAP-087
GAP-088
GAP-089
GAP-090
GAP-091
GAP-092
GAP-093
GAP-094
GAP-095
GAP-096
GAP-097
GAP-098
GAP-099
GAP-100
GAP-101
GAP-102
GAP-103
GAP-104
GAP-105
GAP-106
GAP-107
GAP-108
GAP-109
GAP-110
GAP-111
GAP-112
GAP-113
GAP-114
GAP-115
GAP-116
GAP-117
GAP-118
GAP-119
GAP-120
GAP-121
GAP-122
GAP-123
GAP-124
GAP-125
GAP-126
GAP-127
GAP-128
GAP-129
GAP-130
GAP-131
GAP-132
GAP-133
GAP-134
GAP-135
GAP-136
GAP-137
GAP-138
GAP-139
GAP-140
GAP-141
GAP-142
GAP-143
GAP-144
GAP-145
GAP-146
GAP-147
GAP-148
GAP-149
GAP-150
GAP-151
GAP-152
GAP-153
GAP-154
GAP-155
GAP-156
GAP-157
GAP-158
GAP-159
GAP-160
GAP-161
GAP-162
GAP-163
GAP-164
GAP-165
GAP-166
GAP-167
GAP-168
GAP-169
GAP-170
GAP-171
GAP-172
GAP-173
GAP-174
GAP-175
GAP-176
GAP-177
GAP-178
GAP-179
GAP-180
GAP-181
GAP-182
GAP-183
GAP-184
GAP-185
GAP-186
GAP-187
GAP-188
GAP-189
GAP-190
GAP-191
GAP-192
GAP-193
GAP-194
GAP-195
GAP-196
GAP-197
GAP-198
GAP-199
GAP-200

## Risk Register
CRYPTOGRAPHY RISK REGISTER Consolidated risk assessment for cryptographic control failures
Risk Summary Dashboard
Risk Distribution
Risk Category | Count | Percentage | Risk Exposure
Critical | 0 | 0% | 0
High | 0 | 0% | 0
Medium | 0 | 0% | 0
Low | 0 | 0% | 0
TOTAL | 0 | 100% | 0
Risk By Assessment Area
Assessment Area | Critical | High | Medium | Low | Total Risk Exposure | Avg Risk Score
Data Transmission |  |  |  |  | 0 | 0
Data Storage |  |  |  |  | 0 | 0
Authentication |  |  |  |  | 0 | 0
Key Management |  |  |  |  | 0 | 0
DETAILED RISK REGISTER
RISK-001 | GAP-DAT-002 | Security | Security risk due to: URGENT: Decommission or upgrade... | legacy.company.com | Medium | High | High | Open | Mitigate through Yes... | Residual Risk Score | Risk Response | Risk Owner | Risk Status | Target Risk Score | Review Date | Last Review Date | Next Review Due
RISK-002 | GAP-DAT-007 | Security | Security risk due to: Replace with valid cert... | backup.internal | Medium | High | High | Open | Mitigate through Yes...
RISK-003 | GAP-DAT-012 | Security | Security risk due to: URGENT: Migrate to SFTP... | Legacy FTP | Medium | High | High | Open | Mitigate through Yes...
RISK-004 | GAP-DAT-014 | Security | Security risk due to: Upgrade: TLS 1.3 + MFA + AES-256... | Contractor VPN (OpenVPN) | Medium | High | High | Open | Mitigate through Yes...
RISK-005 | GAP-DAT-016 | Security | Security risk due to: Implement key management... | IoT Devices | Medium | High | High | Open | Mitigate through Yes...
RISK-006 | GAP-DAT-018 | Security | Security risk due to: URGENT: Enable NLA + TLS 1.3... | Legacy Systems | Medium | High | High | Open | Mitigate through Yes...
RISK-007 | GAP-DAT-022 | Security | Security risk due to: Upgrade WPA3 + 802.1X... | Warehouse WiFi | Medium | High | High | Open | Mitigate through Yes...
RISK-008 | GAP-DAT-003 | Security | Security risk due to: Enroll in MDM or decommission... | Test Devices (50 units) | Medium | High | High | Open | Mitigate through Yes...
RISK-009 | GAP-DAT-004 | Security | Security risk due to: Replace or decommission... | Legacy Tablets | Medium | High | High | Open | Mitigate through Yes...
RISK-010 | GAP-DAT-006 | Security | Security risk due to: Enforce encryption policy... | Contractor Laptops (80 units) | Medium | High | High | Open | Mitigate through Yes...
RISK-011 | GAP-DAT-007 | Security | Security risk due to: Upgrade or decommission... | Legacy Desktops (50 units) | Medium | High | High | Open | Mitigate through Yes...
RISK-012 | GAP-DAT-009 | Security | Security risk due to: Migrate or decommission... | Legacy Unix Servers (20 units) | Medium | High | High | Open | Mitigate through Yes...
RISK-013 | GAP-DAT-015 | Security | Security risk due to: Implement encryption... | Test Databases | Medium | High | High | Open | Mitigate through Yes...
RISK-014 | GAP-DAT-017 | Security | Security risk due to: Migrate to encrypted solution... | Legacy Backup System | Medium | High | High | Open | Mitigate through Yes...
RISK-015 | GAP-DAT-020 | Security | Security risk due to: Block standard USB via GPO... | Standard USB Drives | Medium | High | High | Open | Mitigate through Yes...
RISK-016 | GAP-AUT-001 | Security | Security risk due to: Migrate or decommission... | Legacy Applications | Medium | High | High | Open | Mitigate through Yes...
RISK-017 | GAP-AUT-003 | Security | Security risk due to: Implement MFA proxy... | Legacy Systems | Medium | High | High | Open | Mitigate through Yes...
RISK-018 | GAP-AUT-007 | Security | Security risk due to: Modernize authentication... | Legacy Service Accounts | Medium | High | High | Open | Mitigate through Yes...
RISK-019 | GAP-AUT-009 | Security | Security risk due to: Implement SSO proxy... | Legacy Apps (No SSO) | Medium | High | High | Open | Mitigate through Yes...
RISK-020 | GAP-KEY-001 | Security | Security risk due to: Migrate to AES-256... | Legacy DES Keys | Medium | High | High | Open | Mitigate through Yes...
RISK-021 | GAP-KEY-003 | Security | Security risk due to: Implement Vault for dev... | Development Keys (local) | Medium | High | High | Open | Mitigate through Yes...
RISK-022 | GAP-KEY-005 | Security | Security risk due to: Enable auto-rotation... | Azure Storage Keys | Medium | High | High | Open | Mitigate through Yes...
RISK-023 | GAP-KEY-009 | Security | Security risk due to: Replace with proper PKI... | Legacy Self-Signed Certs | Medium | High | High | Open | Mitigate through Yes...
RISK-023
RISK-024
RISK-025
RISK-026
RISK-027
RISK-028
RISK-029
RISK-030
RISK-031
RISK-032
RISK-033
RISK-034
RISK-035
RISK-036
RISK-037
RISK-038
RISK-039
RISK-040
RISK-041
RISK-042
RISK-043
RISK-044
RISK-045
RISK-046
RISK-047
RISK-048
RISK-049
RISK-050
RISK-051
RISK-052
RISK-053
RISK-054
RISK-055
RISK-056
RISK-057
RISK-058
RISK-059
RISK-060
RISK-061
RISK-062
RISK-063
RISK-064
RISK-065
RISK-066
RISK-067
RISK-068
RISK-069
RISK-070
RISK-071
RISK-072
RISK-073
RISK-074
RISK-075
RISK-076
RISK-077
RISK-078
RISK-079
RISK-080
RISK-081
RISK-082
RISK-083
RISK-084
RISK-085
RISK-086
RISK-087
RISK-088
RISK-089
RISK-090
RISK-091
RISK-092
RISK-093
RISK-094
RISK-095
RISK-096
RISK-097
RISK-098
RISK-099
RISK-100

## Remediation Roadmap
CRYPTOGRAPHY REMEDIATION ROADMAP Action plan for closing identified gaps and reducing risk
Roadmap Summary - Overall Progress
Metric | Value | Target | Status
Total Remediation Items | 60 | N/A
Completed | 0 | -
In Progress | 0 | -
Not Started | 0 | -
Overdue | 0 | 0
On Schedule | 0 | 100%
Total Budget Required | 0 | -
Budget Allocated |  | -
Budget Utilized | 0 | -
Progress by Assessment Area
Assessment Area | Total Items | Completed | In Progress | Not Started | % Complete | On-Time %
Data Transmission | 0 | 0 | 0 | 0 | 0%
Data Storage | 0 | 0 | 0 | 0 | 0%
Authentication | 0 | 0 | 0 | 0 | 0%
Key Management | 0 | 0 | 0 | 0 | 0%
REMEDIATION TIMELINE BY QUARTER
(Gantt chart visualization - use conditional formatting or insert chart manually)
DETAILED REMEDIATION REGISTER
Remediation ID | Gap ID (Link) | Risk ID (Link) | Assessment Area | Remediation Action | Action Type | Priority | Current Status | % Complete | Responsible Person | Supporting Team | Start Date | Target Date | Actual Completion | Days Remaining | On Schedule | Dependencies | Budget Required | Budget Approved | Actual Cost | Vendor/Resource | Success Criteria | Verification Method | Completion Evidence | Notes/Comments | Last Updated
REM-001 | [14 empty] | On Track | [9 empty] | 46035
REM-002 | [14 empty] | On Track | [9 empty] | 46035
REM-003 | [14 empty] | On Track | [9 empty] | 46035
REM-004 | [14 empty] | On Track | [9 empty] | 46035
REM-005 | [14 empty] | On Track | [9 empty] | 46035
REM-006 | [14 empty] | On Track | [9 empty] | 46035
REM-007 | [14 empty] | On Track | [9 empty] | 46035
REM-001 | GAP-DAT-001 | Data Transmission | mail.company.com | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-002 | GAP-DAT-002 | Data Transmission | legacy.company.com | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-003 | GAP-DAT-003 | Data Transmission | vpn.company.com | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-004 | GAP-DAT-004 | Data Transmission | test.company.com | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-005 | GAP-DAT-005 | Data Transmission | confluence.internal | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-006 | GAP-DAT-006 | Data Transmission | jira.internal | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-007 | GAP-DAT-007 | Data Transmission | backup.internal | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-008 | GAP-DAT-008 | Data Transmission | Microsoft 365 | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-009 | GAP-DAT-009 | Data Transmission | Internal Mail Server | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-010 | GAP-DAT-010 | Data Transmission | Internal Approvals | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-011 | GAP-DAT-011 | Data Transmission | Email Signatures | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-012 | GAP-DAT-012 | Data Transmission | Legacy FTP | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-013 | GAP-DAT-013 | Data Transmission | Site-to-Site VPN (IPSec) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-014 | GAP-DAT-014 | Data Transmission | Contractor VPN (OpenVPN) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-015 | GAP-DAT-015 | Data Transmission | Network Devices | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-016 | GAP-DAT-016 | Data Transmission | IoT Devices | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-017 | GAP-DAT-017 | Data Transmission | Windows Workstations | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-018 | GAP-DAT-018 | Data Transmission | Legacy Systems | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-019 | GAP-DAT-019 | Data Transmission | Legacy SOAP API | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-020 | GAP-DAT-020 | Data Transmission | Oracle Database | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-021 | GAP-DAT-021 | Data Transmission | IoT WiFi | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-022 | GAP-DAT-022 | Data Transmission | Warehouse WiFi | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-023 | GAP-DAT-001 | Data Storage | BYOD iPhones (enrolled) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-024 | GAP-DAT-002 | Data Storage | BYOD Android (enrolled) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-025 | GAP-DAT-003 | Data Storage | Test Devices (50 units) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-026 | GAP-DAT-004 | Data Storage | Legacy Tablets | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-027 | GAP-DAT-005 | Data Storage | Linux Workstations (100 units) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-028 | GAP-DAT-006 | Data Storage | Contractor Laptops (80 units) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-029 | GAP-DAT-007 | Data Storage | Legacy Desktops (50 units) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-030 | GAP-DAT-008 | Data Storage | Development Servers (50 units) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-031 | GAP-DAT-009 | Data Storage | Legacy Unix Servers (20 units) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-032 | GAP-DAT-010 | Data Storage | MongoDB Analytics (6 nodes) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-033 | GAP-DAT-011 | Data Storage | Redis Cache Cluster | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-034 | GAP-DAT-012 | Data Storage | Oracle Enterprise (4 nodes) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-035 | GAP-DAT-013 | Data Storage | Cassandra Cluster (8 nodes) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-036 | GAP-DAT-014 | Data Storage | MariaDB Prod (6 nodes) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-037 | GAP-DAT-015 | Data Storage | Test Databases | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-038 | GAP-DAT-016 | Data Storage | Personal Backup (Time Machine) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-039 | GAP-DAT-017 | Data Storage | Legacy Backup System | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-040 | GAP-DAT-018 | Data Storage | Corporate SD Cards | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-041 | GAP-DAT-019 | Data Storage | DVD/CD Media (archived) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-042 | GAP-DAT-020 | Data Storage | Standard USB Drives | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-043 | GAP-AUT-001 | Authentication | Legacy Applications | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-044 | GAP-AUT-002 | Authentication | Developer Systems | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-045 | GAP-AUT-003 | Authentication | Legacy Systems | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-046 | GAP-AUT-004 | Authentication | Email Signing (S/MIME) | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-047 | GAP-AUT-005 | Authentication | AD Group Managed Service Accounts | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-048 | GAP-AUT-006 | Authentication | Database Service Accounts | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-049 | GAP-AUT-007 | Authentication | Legacy Service Accounts | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-050 | GAP-AUT-008 | Authentication | Custom Apps with SSO | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-051 | GAP-AUT-009 | Authentication | Legacy Apps (No SSO) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-052 | GAP-KEY-001 | Key Management | Legacy DES Keys | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-053 | GAP-KEY-002 | Key Management | SSH Private Keys | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-054 | GAP-KEY-003 | Key Management | Development Keys (local) | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-055 | GAP-KEY-004 | Key Management | Database Encryption Keys | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-056 | GAP-KEY-005 | Key Management | Azure Storage Keys | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-057 | GAP-KEY-006 | Key Management | SSH Host Keys | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-058 | GAP-KEY-007 | Key Management | Personal SSH Keys | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-059 | GAP-KEY-008 | Key Management | S/MIME Certificates | Yes | High | Planned |  | 2026-01-13 | 2026-03-14 | [5 empty] | On Track | [9 empty] | 46035
REM-060 | GAP-KEY-009 | Key Management | Legacy Self-Signed Certs | Yes | Critical | Planned |  | 2026-01-13 | 2026-02-12 | [5 empty] | On Track | [9 empty] | 46035
REM-068 | [14 empty] | On Track | [9 empty] | 46035
REM-069 | [14 empty] | On Track | [9 empty] | 46035
REM-070 | [14 empty] | On Track | [9 empty] | 46035
REM-071 | [14 empty] | On Track | [9 empty] | 46035
REM-072 | [14 empty] | On Track | [9 empty] | 46035
REM-073 | [14 empty] | On Track | [9 empty] | 46035
REM-074 | [14 empty] | On Track | [9 empty] | 46035
REM-075 | [14 empty] | On Track | [9 empty] | 46035
REM-076 | [14 empty] | On Track | [9 empty] | 46035
REM-077 | [14 empty] | On Track | [9 empty] | 46035
REM-078 | [14 empty] | On Track | [9 empty] | 46035
REM-079 | [14 empty] | On Track | [9 empty] | 46035
REM-080 | [14 empty] | On Track | [9 empty] | 46035
REM-081 | [14 empty] | On Track | [9 empty] | 46035
REM-082 | [14 empty] | On Track | [9 empty] | 46035
REM-083 | [14 empty] | On Track | [9 empty] | 46035
REM-084 | [14 empty] | On Track | [9 empty] | 46035
REM-085 | [14 empty] | On Track | [9 empty] | 46035
REM-086 | [14 empty] | On Track | [9 empty] | 46035
REM-087 | [14 empty] | On Track | [9 empty] | 46035
REM-088 | [14 empty] | On Track | [9 empty] | 46035
REM-089 | [14 empty] | On Track | [9 empty] | 46035
REM-090 | [14 empty] | On Track | [9 empty] | 46035
REM-091 | [14 empty] | On Track | [9 empty] | 46035
REM-092 | [14 empty] | On Track | [9 empty] | 46035
REM-093 | [14 empty] | On Track | [9 empty] | 46035
REM-094 | [14 empty] | On Track | [9 empty] | 46035
REM-095 | [14 empty] | On Track | [9 empty] | 46035
REM-096 | [14 empty] | On Track | [9 empty] | 46035
REM-097 | [14 empty] | On Track | [9 empty] | 46035
REM-098 | [14 empty] | On Track | [9 empty] | 46035
REM-099 | [14 empty] | On Track | [9 empty] | 46035
REM-100 | [14 empty] | On Track | [9 empty] | 46035
REM-101 | [14 empty] | On Track | [9 empty] | 46035
REM-102 | [14 empty] | On Track | [9 empty] | 46035
REM-103 | [14 empty] | On Track | [9 empty] | 46035
REM-104 | [14 empty] | On Track | [9 empty] | 46035
REM-105 | [14 empty] | On Track | [9 empty] | 46035
REM-106 | [14 empty] | On Track | [9 empty] | 46035
REM-107 | [14 empty] | On Track | [9 empty] | 46035
REM-108 | [14 empty] | On Track | [9 empty] | 46035
REM-109 | [14 empty] | On Track | [9 empty] | 46035
REM-110 | [14 empty] | On Track | [9 empty] | 46035
REM-111 | [14 empty] | On Track | [9 empty] | 46035
REM-112 | [14 empty] | On Track | [9 empty] | 46035
REM-113 | [14 empty] | On Track | [9 empty] | 46035
REM-114 | [14 empty] | On Track | [9 empty] | 46035
REM-115 | [14 empty] | On Track | [9 empty] | 46035
REM-116 | [14 empty] | On Track | [9 empty] | 46035
REM-117 | [14 empty] | On Track | [9 empty] | 46035
REM-118 | [14 empty] | On Track | [9 empty] | 46035
REM-119 | [14 empty] | On Track | [9 empty] | 46035
REM-120 | [14 empty] | On Track | [9 empty] | 46035
REM-121 | [14 empty] | On Track | [9 empty] | 46035
REM-122 | [14 empty] | On Track | [9 empty] | 46035
REM-123 | [14 empty] | On Track | [9 empty] | 46035
REM-124 | [14 empty] | On Track | [9 empty] | 46035
REM-125 | [14 empty] | On Track | [9 empty] | 46035
REM-126 | [14 empty] | On Track | [9 empty] | 46035
REM-127 | [14 empty] | On Track | [9 empty] | 46035
REM-128 | [14 empty] | On Track | [9 empty] | 46035
REM-129 | [14 empty] | On Track | [9 empty] | 46035
REM-130 | [14 empty] | On Track | [9 empty] | 46035
REM-131 | [14 empty] | On Track | [9 empty] | 46035
REM-132 | [14 empty] | On Track | [9 empty] | 46035
REM-133 | [14 empty] | On Track | [9 empty] | 46035
REM-134 | [14 empty] | On Track | [9 empty] | 46035
REM-135 | [14 empty] | On Track | [9 empty] | 46035
REM-136 | [14 empty] | On Track | [9 empty] | 46035
REM-137 | [14 empty] | On Track | [9 empty] | 46035
REM-138 | [14 empty] | On Track | [9 empty] | 46035
REM-139 | [14 empty] | On Track | [9 empty] | 46035
REM-140 | [14 empty] | On Track | [9 empty] | 46035
REM-141 | [14 empty] | On Track | [9 empty] | 46035
REM-142 | [14 empty] | On Track | [9 empty] | 46035
REM-143 | [14 empty] | On Track | [9 empty] | 46035
REM-144 | [14 empty] | On Track | [9 empty] | 46035
REM-145 | [14 empty] | On Track | [9 empty] | 46035
REM-146 | [14 empty] | On Track | [9 empty] | 46035
REM-147 | [14 empty] | On Track | [9 empty] | 46035
REM-148 | [14 empty] | On Track | [9 empty] | 46035
REM-149 | [14 empty] | On Track | [9 empty] | 46035
REM-150 | [14 empty] | On Track | [9 empty] | 46035
REM-151 | [14 empty] | On Track | [9 empty] | 46035
REM-152 | [14 empty] | On Track | [9 empty] | 46035
REM-153 | [14 empty] | On Track | [9 empty] | 46035
REM-154 | [14 empty] | On Track | [9 empty] | 46035
REM-155 | [14 empty] | On Track | [9 empty] | 46035
REM-156 | [14 empty] | On Track | [9 empty] | 46035
REM-157 | [14 empty] | On Track | [9 empty] | 46035
REM-158 | [14 empty] | On Track | [9 empty] | 46035
REM-159 | [14 empty] | On Track | [9 empty] | 46035
REM-160 | [14 empty] | On Track | [9 empty] | 46035
REM-161 | [14 empty] | On Track | [9 empty] | 46035
REM-162 | [14 empty] | On Track | [9 empty] | 46035
REM-163 | [14 empty] | On Track | [9 empty] | 46035
REM-164 | [14 empty] | On Track | [9 empty] | 46035
REM-165 | [14 empty] | On Track | [9 empty] | 46035
REM-166 | [14 empty] | On Track | [9 empty] | 46035
REM-167 | [14 empty] | On Track | [9 empty] | 46035
REM-168 | [14 empty] | On Track | [9 empty] | 46035
REM-169 | [14 empty] | On Track | [9 empty] | 46035
REM-170 | [14 empty] | On Track | [9 empty] | 46035
REM-171 | [14 empty] | On Track | [9 empty] | 46035
REM-172 | [14 empty] | On Track | [9 empty] | 46035
REM-173 | [14 empty] | On Track | [9 empty] | 46035
REM-174 | [14 empty] | On Track | [9 empty] | 46035
REM-175 | [14 empty] | On Track | [9 empty] | 46035
REM-176 | [14 empty] | On Track | [9 empty] | 46035
REM-177 | [14 empty] | On Track | [9 empty] | 46035
REM-178 | [14 empty] | On Track | [9 empty] | 46035
REM-179 | [14 empty] | On Track | [9 empty] | 46035
REM-180 | [14 empty] | On Track | [9 empty] | 46035
REM-181 | [14 empty] | On Track | [9 empty] | 46035
REM-182 | [14 empty] | On Track | [9 empty] | 46035
REM-183 | [14 empty] | On Track | [9 empty] | 46035
REM-184 | [14 empty] | On Track | [9 empty] | 46035
REM-185 | [14 empty] | On Track | [9 empty] | 46035
REM-186 | [14 empty] | On Track | [9 empty] | 46035
REM-187 | [14 empty] | On Track | [9 empty] | 46035
REM-188 | [14 empty] | On Track | [9 empty] | 46035
REM-189 | [14 empty] | On Track | [9 empty] | 46035
REM-190 | [14 empty] | On Track | [9 empty] | 46035
REM-191 | [14 empty] | On Track | [9 empty] | 46035
REM-192 | [14 empty] | On Track | [9 empty] | 46035
REM-193 | [14 empty] | On Track | [9 empty] | 46035
REM-194 | [14 empty] | On Track | [9 empty] | 46035
REM-195 | [14 empty] | On Track | [9 empty] | 46035
REM-196 | [14 empty] | On Track | [9 empty] | 46035
REM-197 | [14 empty] | On Track | [9 empty] | 46035
REM-198 | [14 empty] | On Track | [9 empty] | 46035
REM-199 | [14 empty] | On Track | [9 empty] | 46035
REM-200 | [14 empty] | On Track | [9 empty] | 46035
Formulas:
Days Remaining = IF([Current Status]="Completed",0,IF(ISBLANK([Target Date]),"",[Target Date]-TODAY()))

## KPIs & Metrics
KEY PERFORMANCE INDICATORS & METRICS Cryptography program effectiveness measurement
COMPLIANCE METRICS
KPI | Current Value | Target | Threshold | Status | Trend | Last Quarter | YoY Change
Overall Cryptography Compliance Rate | 79.1% | ≥95% | 90%
Data Transmission Encryption Coverage |  | 100% | 95%
Data at Rest Encryption Coverage |  | 100% | 95%
Strong Authentication Coverage |  | ≥90% | 80%
Key Management Compliance |  | ≥95% | 90%
Algorithm Compliance Rate |  | 100% | 98%
Certificate Validity Compliance |  | 100% | 95%
Password Hashing Compliance |  | 100% | 100%
Service Account Security |  | ≥90% | 85%
SSO Coverage |  | ≥80% | 70%
MFA Enrollment - All Users |  | 100% | 95%
MFA Enrollment - Administrators |  | 100% | 100%
Policy Compliance Score |  | ≥95% | 90%
Audit Findings - Open |  | 0 | ≤3
Compliance Exceptions |  | ≤5 | ≤10
RISK METRICS
KPI | Current Value | Target | Threshold | Status | Trend | Last Quarter | YoY Change
Critical Risks - Open | 0 | 0 | 0
High Risks - Open | 0 | ≤5 | ≤10
Average Risk Score | #DIV/0! | <10 | <15
Risk Reduction Rate |  | ≥20% per Q | ≥10%
Residual Risk Exposure | 0 | <100 | <200
Risks Accepted (No Remediation) | 0 | ≤5 | ≤10
Risks Transferred |  | - | -
Time to Risk Identification (Avg Days) |  | ≤7 | ≤14
Time to Risk Remediation (Avg Days) |  | ≤90 | ≤120
Overdue Risks |  | 0 | ≤2
REMEDIATION METRICS
KPI | Current Value | Target | Threshold | Status | Trend | Last Quarter | YoY Change
Total Open Gaps | 200 | ≤10 | ≤20
Critical Gaps - Open | 0 | 0 | 0
High Priority Gaps - Open | 0 | ≤5 | ≤10
Gaps Closed This Quarter |  | ≥10 | ≥5
Gap Closure Rate | 0% | ≥80% | ≥70%
Remediation On-Time % |  | ≥90% | ≥80%
Overdue Remediation Items | 0 | 0 | ≤3
Average Time to Remediation (Days) |  | ≤90 | ≤120
Budget Utilization Rate |  | 90-100% | 80-110%
Remediation Success Rate |  | ≥95% | ≥90%
Recurring Gaps |  | 0 | ≤2
TECHNICAL IMPLEMENTATION METRICS
KPI | Current Value | Target | Threshold | Status | Trend | Last Quarter | YoY Change
Systems Using Approved Algorithms |  | 100% | 98%
Systems Using Weak/Legacy Crypto |  | 0 | ≤2
TLS 1.3 Adoption Rate |  | ≥80% | ≥60%
TLS 1.2+ Coverage |  | 100% | 100%
Certificate Auto-Renewal Rate |  | ≥90% | ≥75%
Certificates Expiring <30 Days |  | 0 | ≤5
Expired Certificates |  | 0 | 0
Self-Signed Certs in Production |  | 0 | 0
Key Rotation Compliance |  | ≥95% | ≥90%
Keys Stored in HSM/KMS |  | ≥90% | ≥80%
FIPS 140-2 Validated Modules |  | ≥80% | ≥70%
Database Encryption (TDE) Coverage |  | 100% | 95%
Disk Encryption Coverage - Endpoints |  | 100% | 98%
Disk Encryption Coverage - Servers |  | 100% | 95%
Backup Encryption Coverage |  | 100% | 100%

## Evidence Register
CONSOLIDATED EVIDENCE REGISTER Central repository for all cryptography compliance evidence
Evidence Summary Statistics
Assessment Area | Total Evidence Items | Verified | Pending Verification | Not Verified | Verification %
Data Transmission | 37 | 0 | 0 | 0 | 0%
Data Storage | 28 | 0 | 0 | 0 | 0%
Authentication | 20 | 0 | 0 | 0 | 0%
Key Management | 22 | 0 | 0 | 0 | 0%
TOTAL | 107 | 0 | 0 | 0 | 0
DETAILED EVIDENCE REGISTER
Evidence ID | Assessment Area | Source Document | Gap ID (Link) | Control Reference | Evidence Type | Evidence Description | Evidence Location/Path | Date Collected | Collected By | Verification Status | Verified By | Verification Date | Retention Period | Destruction Date | Classification | Accessibility | Related Risk ID | Related Remediation ID | Audit Reference | Notes/Comments | Last Updated
EVD-824.1-001 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | SSL Labs Security Report - www.company.com | Technical Report | 1.1 External HTTPS-TLS | SharePoint/Evidence/TLS | 2026-01-10 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-002 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Certificate Inventory Export | Spreadsheet | 1.1 External HTTPS-TLS | SharePoint/Evidence/Certificates | 2026-01-10 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-003 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Let's Encrypt Auto-Renewal Logs | Log File | 1.1 External HTTPS-TLS | S3/evidence/certbot-logs | 2026-01-10 | DevOps | 1 year | Current | [9 empty] | 46035
EVD-824.1-004 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | AWS ACM Certificate Configuration | Screenshot | 1.1 External HTTPS-TLS | SharePoint/Evidence/AWS | 2026-01-10 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-005 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Internal PKI Certificate Policy | Policy Document | 1.2 Internal HTTPS-TLS | SharePoint/Policies | 2025-06-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.1-006 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | AD Certificate Services Audit Report | Audit Report | 1.2 Internal HTTPS-TLS | SharePoint/Audits/2025 | 2025-12-15 | Internal Audit | 7 years | Current | [9 empty] | 46035
EVD-824.1-007 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | M365 Admin Center - S/MIME Adoption Report | Dashboard Export | 2.1 Email Encryption | SharePoint/Evidence/M365 | 2026-01-09 | IT Admin | 1 year | Current | [9 empty] | 46035
EVD-824.1-008 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Google Workspace Security Settings | Screenshot | 2.1 Email Encryption | SharePoint/Evidence/Google | 2026-01-09 | IT Admin | 2 years | Current | [9 empty] | 46035
EVD-824.1-009 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Postfix TLS Configuration File | Config File | 2.1 Email Encryption | Git/configs/postfix | 2025-11-20 | Email Admin | 2 years | Current | [9 empty] | 46035
EVD-824.1-010 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Executive S/MIME Certificate Audit | Audit Report | 2.1 Email Encryption | SharePoint/Audits/Certs | 2025-12-01 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-011 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | DocuSign Audit Trail Report | Audit Log | 2.2 Digital Signatures | DocuSign/Audit-Trails | 2026-01-08 | Legal Team | 7 years | Current | [9 empty] | 46035
EVD-824.1-012 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Adobe Sign Security Configuration | Screenshot | 2.2 Digital Signatures | SharePoint/Evidence/Adobe | 2026-01-08 | Legal Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-013 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Code Signing Certificate - YubiKey HSM | Certificate Copy | 2.2 Digital Signatures | PKI/Code-Signing | 2025-09-15 | DevOps | 5 years | Current | [9 empty] | 46035
EVD-824.1-014 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | CI/CD Pipeline Signing Logs | Log Export | 2.2 Digital Signatures | Jenkins/Logs/Signing | 2026-01-07 | DevOps | 1 year | Current | [9 empty] | 46035
EVD-824.1-015 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | SFTP Server Configuration | Config File | 3.1 File Transfer | Git/configs/sftp | 2025-10-01 | SysAdmin | 2 years | Current | [9 empty] | 46035
EVD-824.1-016 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | FTPS Partner Gateway Access Logs | Log File | 3.1 File Transfer | S3/logs/ftps | 2026-01-10 | Network Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-017 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Legacy FTP Decommission Plan | Project Plan | 3.1 File Transfer | SharePoint/Projects/FTP | 2026-01-05 | IT Manager | 3 years | Current | [9 empty] | 46035
EVD-824.1-018 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | OpenVPN Server Configuration | Config File | 4.1 VPN | Vault/configs/vpn | 2025-11-01 | Network Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-019 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | VPN MFA Enforcement Policy | Policy Document | 4.1 VPN | SharePoint/Policies/VPN | 2025-08-15 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.1-020 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | WireGuard Configuration - Executive VPN | Config File | 4.1 VPN | Vault/configs/wireguard | 2025-12-01 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-021 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | SSH Bastion Host Audit Logs | Log Export | 4.2 SSH | SIEM/ssh-bastion-logs | 2026-01-10 | Security Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-022 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | SSH Key Management Policy | Policy Document | 4.2 SSH | SharePoint/Policies/SSH | 2025-07-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.1-023 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Production Server SSH Key Inventory | Spreadsheet | 4.2 SSH | SharePoint/Inventory/SSH-Keys | 2026-01-08 | SysAdmin | 2 years | Current | [9 empty] | 46035
EVD-824.1-024 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | RDP NLA Configuration - Windows Servers | GPO Export | 4.3 RDP | SharePoint/GPO/RDP | 2025-10-15 | Windows Admin | 2 years | Current | [9 empty] | 46035
EVD-824.1-025 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | RDP MFA Enforcement - Event Logs | Log Export | 4.3 RDP | SIEM/rdp-mfa-events | 2026-01-09 | Security Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-026 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Legacy RDP System Remediation Ticket | Ticket | 4.3 RDP | Jira/SEC-1245 | 2026-01-06 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-027 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | API Gateway Security Configuration | Config Export | 5.1 API Security | Git/configs/api-gateway | 2025-12-10 | API Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-028 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | OAuth 2.0 Implementation Documentation | Technical Doc | 5.1 API Security | Confluence/API-Security | 2025-09-20 | Dev Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-029 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Service Mesh mTLS Configuration | Config File | 5.1 API Security | Git/k8s/istio-config | 2025-11-15 | Platform Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-030 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | PostgreSQL TLS Configuration | Config File | 6.1 Database Connections | Vault/configs/postgres | 2025-10-20 | DBA Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-031 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | MongoDB X.509 Certificate Setup | Technical Doc | 6.1 Database Connections | Confluence/MongoDB | 2025-11-05 | DBA Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-032 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | SQL Server Kerberos Authentication | Config Doc | 6.1 Database Connections | SharePoint/SQL-Security | 2025-09-30 | DBA Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-033 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Corporate WiFi WPA3 Deployment Report | Project Report | 6.2 Wireless Networks | SharePoint/Projects/WiFi | 2025-08-01 | Network Team | 3 years | Current | [9 empty] | 46035
EVD-824.1-034 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | RADIUS Server Configuration | Config File | 6.2 Wireless Networks | Vault/configs/radius | 2025-10-10 | Network Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-035 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Wireless Access Point Inventory | Spreadsheet | 6.2 Wireless Networks | SharePoint/Inventory/WiFi | 2026-01-08 | Network Team | 2 years | Current | [9 empty] | 46035
EVD-824.1-036 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | AWS CloudTrail - VPC Flow Logs | Log Export | 7.1 Cloud Transmission | S3/cloudtrail/2026-01 | 2026-01-10 | Cloud Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-037 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Azure Monitor - Network Security Logs | Dashboard Export | 7.1 Cloud Transmission | Azure/Monitor/Security | 2026-01-10 | Cloud Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-038 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | GCP Cloud Audit Logs - Network | Log Export | 7.1 Cloud Transmission | GCP/Logging/Audit | 2026-01-10 | Cloud Team | 1 year | Current | [9 empty] | 46035
EVD-824.1-039 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | Multi-Cloud VPN Architecture Diagram | Diagram | 7.1 Cloud Transmission | SharePoint/Diagrams/Network | 2025-12-01 | Network Architect | 5 years | Current | [9 empty] | 46035
EVD-824.1-040 | Data Transmission | ISMS-IMP-A.8.24.1.xlsx |  | CDN TLS Configuration - CloudFront | Config Screenshot | 7.1 Cloud Transmission | SharePoint/Evidence/CDN | 2026-01-09 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-001 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | MDM Compliance Report - Mobile Devices | Compliance Report | 1. Mobile Devices | MobileIron/Reports | 2026-01-10 | IT Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-002 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | iOS Encryption Policy Configuration | Configuration Doc | 1. Mobile Devices | SharePoint/MDM/iOS | 2026-01-10 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-003 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Android Encryption Compliance Scan | Scan Report | 1. Mobile Devices | Workspace ONE/Scans | 2026-01-09 | IT Admin | 1 year | Current | [9 empty] | 46035
EVD-824.2-004 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | BYOD Policy Document v2.1 | Policy | 1. Mobile Devices | SharePoint/Policies/BYOD | 2025-06-01 | HR & Security | 5 years | Current | [9 empty] | 46035
EVD-824.2-005 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | BitLocker Deployment Status Report | Deployment Report | 2. Laptops & Workstations | Intune/Reports | 2026-01-10 | Windows Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-006 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | FileVault 2 Compliance - Mac Fleet | Compliance Report | 2. Laptops & Workstations | Jamf/Encryption | 2026-01-10 | Mac Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-007 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | BitLocker Recovery Key Escrow Audit | Audit Report | 2. Laptops & Workstations | AD/BitLocker-Keys | 2025-12-15 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-008 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Linux LUKS Encryption Standards | Technical Standard | 2. Laptops & Workstations | SharePoint/Standards | 2025-08-01 | Linux Team | 5 years | Current | [9 empty] | 46035
EVD-824.2-009 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Server Encryption Audit Q4 2025 | Audit Report | 3. Servers | SharePoint/Audits/Servers | 2025-12-20 | Internal Audit | 7 years | Current | [9 empty] | 46035
EVD-824.2-010 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | VMware VM Encryption Configuration | Config Export | 3. Servers | vCenter/Configs | 2026-01-08 | VMware Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-011 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Kubernetes etcd Encryption Config | YAML Config | 3. Servers | Git/k8s/encryption | 2025-11-15 | K8s Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-012 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | PostgreSQL TDE Implementation Guide | Technical Doc | 4. Databases | Confluence/Database/PG | 2025-09-20 | DBA Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-013 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | MySQL TDE Status Report | Status Report | 4. Databases | SharePoint/DBA/MySQL | 2026-01-09 | DBA Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-014 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | SQL Server TDE Configuration Audit | Audit Report | 4. Databases | SQL-Audit/TDE | 2025-12-10 | DBA Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-015 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | AWS KMS Key Policy - Databases | Policy Doc | 4. Databases | AWS/KMS/Policies | 2025-10-15 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-016 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | MongoDB Encryption at Rest Config | Config File | 4. Databases | Git/mongodb/encryption | 2025-11-01 | DBA Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-017 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | S3 Bucket Encryption Compliance | Compliance Report | 5. Cloud Storage | AWS/S3/Encryption | 2026-01-10 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-018 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Azure Storage Encryption Config | Config Screenshot | 5. Cloud Storage | Azure/Storage/Security | 2026-01-10 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-019 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | GCP CMEK Configuration Guide | Technical Guide | 5. Cloud Storage | GCP/Security/CMEK | 2025-10-01 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.2-020 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | EBS Volume Encryption Status | Status Report | 5. Cloud Storage | AWS/EC2/EBS | 2026-01-09 | Cloud Team | 1 year | Current | [9 empty] | 46035
EVD-824.2-021 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Veeam Backup Encryption Settings | Config Export | 6. Backups | Veeam/Config | 2026-01-08 | Backup Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-022 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | AWS Backup Vault Encryption | Screenshot | 6. Backups | AWS/Backup/Config | 2026-01-10 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-023 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Backup Encryption Policy v3.0 | Policy | 6. Backups | SharePoint/Policies/Backup | 2025-07-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.2-024 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Tape Encryption Key Escrow Procedure | Procedure | 6. Backups | SharePoint/Procedures | 2025-09-15 | Backup Team | 5 years | Current | [9 empty] | 46035
EVD-824.2-025 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | IronKey USB Deployment List | Inventory | 7. Removable Media | SharePoint/Inventory/USB | 2026-01-08 | IT Admin | 2 years | Current | [9 empty] | 46035
EVD-824.2-026 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Removable Media Policy v2.5 | Policy | 7. Removable Media | SharePoint/Policies/Media | 2025-08-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.2-027 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | DLP USB Blocking Configuration | GPO Export | 7. Removable Media | AD/GPO/DLP | 2025-11-20 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.2-028 | Data Storage | ISMS-IMP-A.8.24.2.xlsx |  | Encrypted USB Vendor Comparison | Analysis Doc | 7. Removable Media | SharePoint/Procurement | 2025-10-10 | IT Procurement | 3 years | Current | [9 empty] | 46035
EVD-824.3-001 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Active Directory Password Policy GPO | GPO Export | 1. Password Security | AD/GPO/Password | 2026-01-10 | Windows Admin | 3 years | Current | [9 empty] | 46035
EVD-824.3-002 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Azure AD Password Policy Configuration | Screenshot | 1. Password Security | Azure/AAD/Security | 2026-01-10 | Cloud Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-003 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Linux PAM Configuration Audit | Config Files | 1. Password Security | Linux/PAM/Config | 2026-01-09 | Linux Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-004 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Password Security Standard v3.2 | Standard Document | 1. Password Security | SharePoint/Standards | 2025-08-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.3-005 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Azure MFA Adoption Report | Compliance Report | 2. Multi-Factor Authentication | Azure/MFA/Reports | 2026-01-10 | Security Team | 1 year | Current | [9 empty] | 46035
EVD-824.3-006 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Duo Security Deployment Configuration | Config Export | 2. Multi-Factor Authentication | Duo/Admin/Config | 2026-01-09 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.3-007 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | YubiKey Deployment Inventory | Inventory List | 2. Multi-Factor Authentication | SharePoint/Inventory/MFA | 2026-01-08 | IT Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-008 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | MFA Policy Document v2.5 | Policy | 2. Multi-Factor Authentication | SharePoint/Policies/MFA | 2025-09-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.3-009 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | PIV Smart Card Deployment Guide | Technical Guide | 3. Certificate-Based Auth | SharePoint/Guides/PIV | 2025-10-15 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.3-010 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | PKI Certificate Policy | Policy Document | 3. Certificate-Based Auth | SharePoint/Policies/PKI | 2025-06-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.3-011 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | mTLS Architecture Documentation | Architecture Doc | 3. Certificate-Based Auth | Confluence/mTLS | 2025-11-01 | Platform Team | 3 years | Current | [9 empty] | 46035
EVD-824.3-012 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | S/MIME Certificate Deployment Report | Deployment Report | 3. Certificate-Based Auth | SharePoint/Certificates | 2026-01-09 | Email Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-013 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Azure Managed Identity Implementation | Technical Doc | 4. Service Accounts | Azure/Documentation | 2025-12-01 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.3-014 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | AWS IAM Role Best Practices | Best Practices Doc | 4. Service Accounts | AWS/Documentation | 2025-11-15 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.3-015 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | gMSA Deployment Status Report | Status Report | 4. Service Accounts | AD/gMSA/Reports | 2026-01-08 | Windows Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-016 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Service Account Inventory Q1 2026 | Inventory | 4. Service Accounts | SharePoint/Inventory/SA | 2026-01-10 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.3-017 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Azure AD SSO Configuration | Config Export | 5. SSO & Federation | Azure/AAD/SSO | 2026-01-10 | Cloud Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-018 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | Okta Application Integration List | Integration List | 5. SSO & Federation | Okta/Admin/Apps | 2026-01-09 | IT Admin | 2 years | Current | [9 empty] | 46035
EVD-824.3-019 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | ADFS Federation Configuration | Config Documentation | 5. SSO & Federation | ADFS/Configuration | 2025-12-15 | Identity Team | 3 years | Current | [9 empty] | 46035
EVD-824.3-020 | Authentication | ISMS-IMP-A.8.24.3.xlsx |  | SSO Implementation Standard | Standard Document | 5. SSO & Federation | SharePoint/Standards/SSO | 2025-09-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.4-001 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Key Generation Standard v2.0 | Standard Document | 1. Key Generation | SharePoint/Standards/Keys | 2025-09-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.4-002 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | AWS KMS Key Policy Documentation | Policy Document | 1. Key Generation | AWS/KMS/Policies | 2026-01-10 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-003 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | HashiCorp Vault Key Audit Report | Audit Report | 1. Key Generation | Vault/Audit/Q4-2025 | 2025-12-20 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-004 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Code Signing Key Ceremony Documentation | Ceremony Doc | 1. Key Generation | SharePoint/Ceremonies/Code-Signing | 2025-08-15 | DevOps Team | 7 years | Current | [9 empty] | 46035
EVD-824.4-005 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | YubiKey HSM Deployment Guide | Technical Guide | 1. Key Generation | SharePoint/Guides/HSM | 2025-10-01 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-006 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | AWS ACM Configuration Screenshot | Screenshot | 2. Key Storage | SharePoint/Evidence/ACM | 2026-01-10 | Cloud Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-007 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Azure Key Vault Access Policies | Config Export | 2. Key Storage | Azure/KeyVault/Policies | 2026-01-10 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-008 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Vault Access Control Policies | Policy Document | 2. Key Storage | Vault/Policies | 2025-11-15 | Security Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-009 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Kubernetes etcd Encryption Configuration | Config File | 2. Key Storage | Git/k8s/etcd-encryption | 2025-11-20 | Platform Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-010 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | SSH Key Passphrase Enforcement Policy | Policy | 2. Key Storage | SharePoint/Policies/SSH | 2025-09-01 | Security Team | 5 years | Current | [9 empty] | 46035
EVD-824.4-011 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | TLS Certificate Auto-Renewal Logs | Log File | 3. Key Rotation | CertBot/Logs/2025 | 2026-01-10 | DevOps | 1 year | Current | [9 empty] | 46035
EVD-824.4-012 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Key Rotation Schedule Q1 2026 | Schedule Document | 3. Key Rotation | SharePoint/Schedules/Keys | 2026-01-08 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-013 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Vault Key Rotation Configuration | Config File | 3. Key Rotation | Vault/Config/Rotation | 2025-12-01 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-014 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Azure Storage Key Rotation Remediation Plan | Remediation Plan | 3. Key Rotation | SharePoint/Projects/Azure-Keys | 2026-01-05 | Cloud Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-015 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | HSM Master Key Ceremony Procedure | Procedure Document | 4. Key Backup & Recovery | SharePoint/Procedures/HSM | 2025-07-01 | Security Team | 7 years | Current | [9 empty] | 46035
EVD-824.4-016 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | BitLocker Recovery Key Escrow Audit | Audit Report | 4. Key Backup & Recovery | AD/BitLocker/Audit | 2025-12-15 | Windows Team | 3 years | Current | [9 empty] | 46035
EVD-824.4-017 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Jamf Pro FileVault Key Escrow Config | Config Screenshot | 4. Key Backup & Recovery | Jamf/FileVault/Config | 2026-01-09 | Mac Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-018 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Root CA Key Ceremony Documentation | Ceremony Doc | 4. Key Backup & Recovery | PKI/Root-CA/Ceremony | 2024-06-15 | Security Team | 10 years | Current | [9 empty] | 46035
EVD-824.4-019 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Certificate Inventory System Export | Inventory Export | 5. Certificate Management | CertManager/Inventory | 2026-01-10 | Security Team | 2 years | Current | [9 empty] | 46035
EVD-824.4-020 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Internal PKI Architecture Documentation | Architecture Doc | 5. Certificate Management | SharePoint/Architecture/PKI | 2025-09-20 | Security Architect | 5 years | Current | [9 empty] | 46035
EVD-824.4-021 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | Certificate Expiry Monitoring Dashboard | Dashboard Screenshot | 5. Certificate Management | SharePoint/Evidence/Cert-Monitor | 2026-01-09 | Security Team | 1 year | Current | [9 empty] | 46035
EVD-824.4-022 | Key Management | ISMS-IMP-A.8.24.4.xlsx |  | S/MIME Deployment Status Report | Status Report | 5. Certificate Management | SharePoint/Reports/SMIME | 2026-01-08 | Email Team | 2 years | Current | [9 empty] | 46035
EV-111 | [20 empty] | 46035
EV-112 | [20 empty] | 46035
EV-113 | [20 empty] | 46035
EV-114 | [20 empty] | 46035
EV-115 | [20 empty] | 46035
EV-116 | [20 empty] | 46035
EV-117 | [20 empty] | 46035
EV-118 | [20 empty] | 46035
EV-119 | [20 empty] | 46035
EV-120 | [20 empty] | 46035
EV-121 | [20 empty] | 46035
EV-122 | [20 empty] | 46035
EV-123 | [20 empty] | 46035
EV-124 | [20 empty] | 46035
EV-125 | [20 empty] | 46035
EV-126 | [20 empty] | 46035
EV-127 | [20 empty] | 46035
EV-128 | [20 empty] | 46035
EV-129 | [20 empty] | 46035
EV-130 | [20 empty] | 46035
EV-131 | [20 empty] | 46035
EV-132 | [20 empty] | 46035
EV-133 | [20 empty] | 46035
EV-134 | [20 empty] | 46035
EV-135 | [20 empty] | 46035
EV-136 | [20 empty] | 46035
EV-137 | [20 empty] | 46035
EV-138 | [20 empty] | 46035
EV-139 | [20 empty] | 46035
EV-140 | [20 empty] | 46035
EV-141 | [20 empty] | 46035
EV-142 | [20 empty] | 46035
EV-143 | [20 empty] | 46035
EV-144 | [20 empty] | 46035
EV-145 | [20 empty] | 46035
EV-146 | [20 empty] | 46035
EV-147 | [20 empty] | 46035
EV-148 | [20 empty] | 46035
EV-149 | [20 empty] | 46035
EV-150 | [20 empty] | 46035
EV-151 | [20 empty] | 46035
EV-152 | [20 empty] | 46035
EV-153 | [20 empty] | 46035
EV-154 | [20 empty] | 46035
EV-155 | [20 empty] | 46035
EV-156 | [20 empty] | 46035
EV-157 | [20 empty] | 46035
EV-158 | [20 empty] | 46035
EV-159 | [20 empty] | 46035
EV-160 | [20 empty] | 46035
EV-161 | [20 empty] | 46035
EV-162 | [20 empty] | 46035
EV-163 | [20 empty] | 46035
EV-164 | [20 empty] | 46035
EV-165 | [20 empty] | 46035
EV-166 | [20 empty] | 46035
EV-167 | [20 empty] | 46035
EV-168 | [20 empty] | 46035
EV-169 | [20 empty] | 46035
EV-170 | [20 empty] | 46035
EV-171 | [20 empty] | 46035
EV-172 | [20 empty] | 46035
EV-173 | [20 empty] | 46035
EV-174 | [20 empty] | 46035
EV-175 | [20 empty] | 46035
EV-176 | [20 empty] | 46035
EV-177 | [20 empty] | 46035
EV-178 | [20 empty] | 46035
EV-179 | [20 empty] | 46035
EV-180 | [20 empty] | 46035
EV-181 | [20 empty] | 46035
EV-182 | [20 empty] | 46035
EV-183 | [20 empty] | 46035
EV-184 | [20 empty] | 46035
EV-185 | [20 empty] | 46035
EV-186 | [20 empty] | 46035
EV-187 | [20 empty] | 46035
EV-188 | [20 empty] | 46035
EV-189 | [20 empty] | 46035
EV-190 | [20 empty] | 46035
EV-191 | [20 empty] | 46035
EV-192 | [20 empty] | 46035
EV-193 | [20 empty] | 46035
EV-194 | [20 empty] | 46035
EV-195 | [20 empty] | 46035
EV-196 | [20 empty] | 46035
EV-197 | [20 empty] | 46035
EV-198 | [20 empty] | 46035
EV-199 | [20 empty] | 46035
EV-200 | [20 empty] | 46035
EV-201 | [20 empty] | 46035
EV-202 | [20 empty] | 46035
EV-203 | [20 empty] | 46035
EV-204 | [20 empty] | 46035
EV-205 | [20 empty] | 46035
EV-206 | [20 empty] | 46035
EV-207 | [20 empty] | 46035
EV-208 | [20 empty] | 46035
EV-209 | [20 empty] | 46035
EV-210 | [20 empty] | 46035
EV-211 | [20 empty] | 46035
EV-212 | [20 empty] | 46035
EV-213 | [20 empty] | 46035
EV-214 | [20 empty] | 46035
EV-215 | [20 empty] | 46035
EV-216 | [20 empty] | 46035
EV-217 | [20 empty] | 46035
EV-218 | [20 empty] | 46035
EV-219 | [20 empty] | 46035
EV-220 | [20 empty] | 46035
EV-221 | [20 empty] | 46035
EV-222 | [20 empty] | 46035
EV-223 | [20 empty] | 46035
EV-224 | [20 empty] | 46035
EV-225 | [20 empty] | 46035
EV-226 | [20 empty] | 46035
EV-227 | [20 empty] | 46035
EV-228 | [20 empty] | 46035
EV-229 | [20 empty] | 46035
EV-230 | [20 empty] | 46035
EV-231 | [20 empty] | 46035
EV-232 | [20 empty] | 46035
EV-233 | [20 empty] | 46035
EV-234 | [20 empty] | 46035
EV-235 | [20 empty] | 46035
EV-236 | [20 empty] | 46035
EV-237 | [20 empty] | 46035
EV-238 | [20 empty] | 46035
EV-239 | [20 empty] | 46035
EV-240 | [20 empty] | 46035
EV-241 | [20 empty] | 46035
EV-242 | [20 empty] | 46035
EV-243 | [20 empty] | 46035
EV-244 | [20 empty] | 46035
EV-245 | [20 empty] | 46035
EV-246 | [20 empty] | 46035
EV-247 | [20 empty] | 46035
EV-248 | [20 empty] | 46035
EV-249 | [20 empty] | 46035
EV-250 | [20 empty] | 46035
EV-251 | [20 empty] | 46035
EV-252 | [20 empty] | 46035
EV-253 | [20 empty] | 46035
EV-254 | [20 empty] | 46035
EV-255 | [20 empty] | 46035
EV-256 | [20 empty] | 46035
EV-257 | [20 empty] | 46035
EV-258 | [20 empty] | 46035
EV-259 | [20 empty] | 46035
EV-260 | [20 empty] | 46035
EV-261 | [20 empty] | 46035
EV-262 | [20 empty] | 46035
EV-263 | [20 empty] | 46035
EV-264 | [20 empty] | 46035
EV-265 | [20 empty] | 46035
EV-266 | [20 empty] | 46035
EV-267 | [20 empty] | 46035
EV-268 | [20 empty] | 46035
EV-269 | [20 empty] | 46035
EV-270 | [20 empty] | 46035
EV-271 | [20 empty] | 46035
EV-272 | [20 empty] | 46035
EV-273 | [20 empty] | 46035
EV-274 | [20 empty] | 46035
EV-275 | [20 empty] | 46035
EV-276 | [20 empty] | 46035
EV-277 | [20 empty] | 46035
EV-278 | [20 empty] | 46035
EV-279 | [20 empty] | 46035
EV-280 | [20 empty] | 46035
EV-281 | [20 empty] | 46035
EV-282 | [20 empty] | 46035
EV-283 | [20 empty] | 46035
EV-284 | [20 empty] | 46035
EV-285 | [20 empty] | 46035
EV-286 | [20 empty] | 46035
EV-287 | [20 empty] | 46035
EV-288 | [20 empty] | 46035
EV-289 | [20 empty] | 46035
EV-290 | [20 empty] | 46035
EV-291 | [20 empty] | 46035
EV-292 | [20 empty] | 46035
EV-293 | [20 empty] | 46035
EV-294 | [20 empty] | 46035
EV-295 | [20 empty] | 46035
EV-296 | [20 empty] | 46035
EV-297 | [20 empty] | 46035
EV-298 | [20 empty] | 46035
EV-299 | [20 empty] | 46035
EV-300 | [20 empty] | 46035
EV-301 | [20 empty] | 46035
EV-302 | [20 empty] | 46035
EV-303 | [20 empty] | 46035
EV-304 | [20 empty] | 46035
EV-305 | [20 empty] | 46035
EV-306 | [20 empty] | 46035
EV-307 | [20 empty] | 46035
EV-308 | [20 empty] | 46035
EV-309 | [20 empty] | 46035
EV-310 | [20 empty] | 46035
EV-311 | [20 empty] | 46035
EV-312 | [20 empty] | 46035
EV-313 | [20 empty] | 46035
EV-314 | [20 empty] | 46035
EV-315 | [20 empty] | 46035
EV-316 | [20 empty] | 46035
EV-317 | [20 empty] | 46035
EV-318 | [20 empty] | 46035
EV-319 | [20 empty] | 46035
EV-320 | [20 empty] | 46035
EV-321 | [20 empty] | 46035
EV-322 | [20 empty] | 46035
EV-323 | [20 empty] | 46035
EV-324 | [20 empty] | 46035
EV-325 | [20 empty] | 46035
EV-326 | [20 empty] | 46035
EV-327 | [20 empty] | 46035
EV-328 | [20 empty] | 46035
EV-329 | [20 empty] | 46035
EV-330 | [20 empty] | 46035
EV-331 | [20 empty] | 46035
EV-332 | [20 empty] | 46035
EV-333 | [20 empty] | 46035
EV-334 | [20 empty] | 46035
EV-335 | [20 empty] | 46035
EV-336 | [20 empty] | 46035
EV-337 | [20 empty] | 46035
EV-338 | [20 empty] | 46035
EV-339 | [20 empty] | 46035
EV-340 | [20 empty] | 46035
EV-341 | [20 empty] | 46035
EV-342 | [20 empty] | 46035
EV-343 | [20 empty] | 46035
EV-344 | [20 empty] | 46035
EV-345 | [20 empty] | 46035
EV-346 | [20 empty] | 46035
EV-347 | [20 empty] | 46035
EV-348 | [20 empty] | 46035
EV-349 | [20 empty] | 46035
EV-350 | [20 empty] | 46035
EV-351 | [20 empty] | 46035
EV-352 | [20 empty] | 46035
EV-353 | [20 empty] | 46035
EV-354 | [20 empty] | 46035
EV-355 | [20 empty] | 46035
EV-356 | [20 empty] | 46035
EV-357 | [20 empty] | 46035
EV-358 | [20 empty] | 46035
EV-359 | [20 empty] | 46035
EV-360 | [20 empty] | 46035
EV-361 | [20 empty] | 46035
EV-362 | [20 empty] | 46035
EV-363 | [20 empty] | 46035
EV-364 | [20 empty] | 46035
EV-365 | [20 empty] | 46035
EV-366 | [20 empty] | 46035
EV-367 | [20 empty] | 46035
EV-368 | [20 empty] | 46035
EV-369 | [20 empty] | 46035
EV-370 | [20 empty] | 46035
EV-371 | [20 empty] | 46035
EV-372 | [20 empty] | 46035
EV-373 | [20 empty] | 46035
EV-374 | [20 empty] | 46035
EV-375 | [20 empty] | 46035
EV-376 | [20 empty] | 46035
EV-377 | [20 empty] | 46035
EV-378 | [20 empty] | 46035
EV-379 | [20 empty] | 46035
EV-380 | [20 empty] | 46035
EV-381 | [20 empty] | 46035
EV-382 | [20 empty] | 46035
EV-383 | [20 empty] | 46035
EV-384 | [20 empty] | 46035
EV-385 | [20 empty] | 46035
EV-386 | [20 empty] | 46035
EV-387 | [20 empty] | 46035
EV-388 | [20 empty] | 46035
EV-389 | [20 empty] | 46035
EV-390 | [20 empty] | 46035
EV-391 | [20 empty] | 46035
EV-392 | [20 empty] | 46035
EV-393 | [20 empty] | 46035
EV-394 | [20 empty] | 46035
EV-395 | [20 empty] | 46035
EV-396 | [20 empty] | 46035
EV-397 | [20 empty] | 46035
EV-398 | [20 empty] | 46035
EV-399 | [20 empty] | 46035
EV-400 | [20 empty] | 46035
EV-401 | [20 empty] | 46035
EV-402 | [20 empty] | 46035
EV-403 | [20 empty] | 46035
EV-404 | [20 empty] | 46035
EV-405 | [20 empty] | 46035
EV-406 | [20 empty] | 46035
EV-407 | [20 empty] | 46035
EV-408 | [20 empty] | 46035
EV-409 | [20 empty] | 46035
EV-410 | [20 empty] | 46035
EV-411 | [20 empty] | 46035
EV-412 | [20 empty] | 46035
EV-413 | [20 empty] | 46035
EV-414 | [20 empty] | 46035
EV-415 | [20 empty] | 46035
EV-416 | [20 empty] | 46035
EV-417 | [20 empty] | 46035
EV-418 | [20 empty] | 46035
EV-419 | [20 empty] | 46035
EV-420 | [20 empty] | 46035
EV-421 | [20 empty] | 46035
EV-422 | [20 empty] | 46035
EV-423 | [20 empty] | 46035
EV-424 | [20 empty] | 46035
EV-425 | [20 empty] | 46035
EV-426 | [20 empty] | 46035
EV-427 | [20 empty] | 46035
EV-428 | [20 empty] | 46035
EV-429 | [20 empty] | 46035
EV-430 | [20 empty] | 46035
EV-431 | [20 empty] | 46035
EV-432 | [20 empty] | 46035
EV-433 | [20 empty] | 46035
EV-434 | [20 empty] | 46035
EV-435 | [20 empty] | 46035
EV-436 | [20 empty] | 46035
EV-437 | [20 empty] | 46035
EV-438 | [20 empty] | 46035
EV-439 | [20 empty] | 46035
EV-440 | [20 empty] | 46035
EV-441 | [20 empty] | 46035
EV-442 | [20 empty] | 46035
EV-443 | [20 empty] | 46035
EV-444 | [20 empty] | 46035
EV-445 | [20 empty] | 46035
EV-446 | [20 empty] | 46035
EV-447 | [20 empty] | 46035
EV-448 | [20 empty] | 46035
EV-449 | [20 empty] | 46035
EV-450 | [20 empty] | 46035
EV-451 | [20 empty] | 46035
EV-452 | [20 empty] | 46035
EV-453 | [20 empty] | 46035
EV-454 | [20 empty] | 46035
EV-455 | [20 empty] | 46035
EV-456 | [20 empty] | 46035
EV-457 | [20 empty] | 46035
EV-458 | [20 empty] | 46035
EV-459 | [20 empty] | 46035
EV-460 | [20 empty] | 46035
EV-461 | [20 empty] | 46035
EV-462 | [20 empty] | 46035
EV-463 | [20 empty] | 46035
EV-464 | [20 empty] | 46035
EV-465 | [20 empty] | 46035
EV-466 | [20 empty] | 46035
EV-467 | [20 empty] | 46035
EV-468 | [20 empty] | 46035
EV-469 | [20 empty] | 46035
EV-470 | [20 empty] | 46035
EV-471 | [20 empty] | 46035
EV-472 | [20 empty] | 46035
EV-473 | [20 empty] | 46035
EV-474 | [20 empty] | 46035
EV-475 | [20 empty] | 46035
EV-476 | [20 empty] | 46035
EV-477 | [20 empty] | 46035
EV-478 | [20 empty] | 46035
EV-479 | [20 empty] | 46035
EV-480 | [20 empty] | 46035
EV-481 | [20 empty] | 46035
EV-482 | [20 empty] | 46035
EV-483 | [20 empty] | 46035
EV-484 | [20 empty] | 46035
EV-485 | [20 empty] | 46035
EV-486 | [20 empty] | 46035
EV-487 | [20 empty] | 46035
EV-488 | [20 empty] | 46035
EV-489 | [20 empty] | 46035
EV-490 | [20 empty] | 46035
EV-491 | [20 empty] | 46035
EV-492 | [20 empty] | 46035
EV-493 | [20 empty] | 46035
EV-494 | [20 empty] | 46035
EV-495 | [20 empty] | 46035
EV-496 | [20 empty] | 46035
EV-497 | [20 empty] | 46035
EV-498 | [20 empty] | 46035
EV-499 | [20 empty] | 46035
EV-500 | [20 empty] | 46035
Formulas:
Destruction Date = IF(OR(ISBLANK([Date Collected]),ISBLANK([Retention Period])),"",EDATE([Date Collected],IF([Retention Period]="1 year",12,IF([Retention Period]="3 years",36,IF([Retention Period]="5 years",60,IF([Retention Period]="7 years",84,600))))))

## Action Items & Follow-up
ACTION ITEMS & FOLLOW-UP TRACKER Centralized tracking of all outstanding actions
Action Summary Dashboard
Current Status
Status | Count | Percentage | Overdue Count
Not Started | 0 | 0% | 0
In Progress | 0 | 0% | 0
Blocked | 0 | 0% | 0
Pending Review | 0 | 0% | 0
Completed | 0 | 0% | N/A
TOTAL | 0 | 100% | 0
By Priority
Priority | Open Actions | Overdue | % Complete | Avg Days Open
Critical | 0 | 0
High | 0 | 0
Medium | 0 | 0
Low | 0 | 0
DETAILED ACTION REGISTER
Action ID | Source | Source ID | Action Description | Action Type | Priority | Status | Owner | Supporting Team | Created Date | Due Date | Completed Date | Days Open | Days Remaining | On Time Status | Blocking Issue | Dependencies | Progress % | Last Update Date | Last Update By | Update Notes | Escalation Required | Escalated To | Escalation Date
ACT-001 | [13 empty] | On Time
ACT-002 | [13 empty] | On Time
ACT-003 | [13 empty] | On Time
ACT-004 | [13 empty] | On Time
ACT-005 | [13 empty] | On Time
ACT-006 | [13 empty] | On Time
ACT-007 | [13 empty] | On Time
ACT-008 | [13 empty] | On Time
ACT-009 | [13 empty] | On Time
ACT-010 | [13 empty] | On Time
ACT-011 | [13 empty] | On Time
ACT-012 | [13 empty] | On Time
ACT-013 | [13 empty] | On Time
ACT-014 | [13 empty] | On Time
ACT-015 | [13 empty] | On Time
ACT-016 | [13 empty] | On Time
ACT-017 | [13 empty] | On Time
ACT-018 | [13 empty] | On Time
ACT-019 | [13 empty] | On Time
ACT-020 | [13 empty] | On Time
ACT-021 | [13 empty] | On Time
ACT-022 | [13 empty] | On Time
ACT-023 | [13 empty] | On Time
ACT-024 | [13 empty] | On Time
ACT-025 | [13 empty] | On Time
ACT-026 | [13 empty] | On Time
ACT-027 | [13 empty] | On Time
ACT-028 | [13 empty] | On Time
ACT-029 | [13 empty] | On Time
ACT-030 | [13 empty] | On Time
ACT-031 | [13 empty] | On Time
ACT-032 | [13 empty] | On Time
ACT-033 | [13 empty] | On Time
ACT-034 | [13 empty] | On Time
ACT-035 | [13 empty] | On Time
ACT-036 | [13 empty] | On Time
ACT-037 | [13 empty] | On Time
ACT-038 | [13 empty] | On Time
ACT-039 | [13 empty] | On Time
ACT-040 | [13 empty] | On Time
ACT-041 | [13 empty] | On Time
ACT-042 | [13 empty] | On Time
ACT-043 | [13 empty] | On Time
ACT-044 | [13 empty] | On Time
ACT-045 | [13 empty] | On Time
ACT-046 | [13 empty] | On Time
ACT-047 | [13 empty] | On Time
ACT-048 | [13 empty] | On Time
ACT-049 | [13 empty] | On Time
ACT-050 | [13 empty] | On Time
ACT-051 | [13 empty] | On Time
ACT-052 | [13 empty] | On Time
ACT-053 | [13 empty] | On Time
ACT-054 | [13 empty] | On Time
ACT-055 | [13 empty] | On Time
ACT-056 | [13 empty] | On Time
ACT-057 | [13 empty] | On Time
ACT-058 | [13 empty] | On Time
ACT-059 | [13 empty] | On Time
ACT-060 | [13 empty] | On Time
ACT-061 | [13 empty] | On Time
ACT-062 | [13 empty] | On Time
ACT-063 | [13 empty] | On Time
ACT-064 | [13 empty] | On Time
ACT-065 | [13 empty] | On Time
ACT-066 | [13 empty] | On Time
ACT-067 | [13 empty] | On Time
ACT-068 | [13 empty] | On Time
ACT-069 | [13 empty] | On Time
ACT-070 | [13 empty] | On Time
ACT-071 | [13 empty] | On Time
ACT-072 | [13 empty] | On Time
ACT-073 | [13 empty] | On Time
ACT-074 | [13 empty] | On Time
ACT-075 | [13 empty] | On Time
ACT-076 | [13 empty] | On Time
ACT-077 | [13 empty] | On Time
ACT-078 | [13 empty] | On Time
ACT-079 | [13 empty] | On Time
ACT-080 | [13 empty] | On Time
ACT-081 | [13 empty] | On Time
ACT-082 | [13 empty] | On Time
ACT-083 | [13 empty] | On Time
ACT-084 | [13 empty] | On Time
ACT-085 | [13 empty] | On Time
ACT-086 | [13 empty] | On Time
ACT-087 | [13 empty] | On Time
ACT-088 | [13 empty] | On Time
ACT-089 | [13 empty] | On Time
ACT-090 | [13 empty] | On Time
ACT-091 | [13 empty] | On Time
ACT-092 | [13 empty] | On Time
ACT-093 | [13 empty] | On Time
ACT-094 | [13 empty] | On Time
ACT-095 | [13 empty] | On Time
ACT-096 | [13 empty] | On Time
ACT-097 | [13 empty] | On Time
ACT-098 | [13 empty] | On Time
ACT-099 | [13 empty] | On Time
ACT-100 | [13 empty] | On Time
ACT-101 | [13 empty] | On Time
ACT-102 | [13 empty] | On Time
ACT-103 | [13 empty] | On Time
ACT-104 | [13 empty] | On Time
ACT-105 | [13 empty] | On Time
ACT-106 | [13 empty] | On Time
ACT-107 | [13 empty] | On Time
ACT-108 | [13 empty] | On Time
ACT-109 | [13 empty] | On Time
ACT-110 | [13 empty] | On Time
ACT-111 | [13 empty] | On Time
ACT-112 | [13 empty] | On Time
ACT-113 | [13 empty] | On Time
ACT-114 | [13 empty] | On Time
ACT-115 | [13 empty] | On Time
ACT-116 | [13 empty] | On Time
ACT-117 | [13 empty] | On Time
ACT-118 | [13 empty] | On Time
ACT-119 | [13 empty] | On Time
ACT-120 | [13 empty] | On Time
ACT-121 | [13 empty] | On Time
ACT-122 | [13 empty] | On Time
ACT-123 | [13 empty] | On Time
ACT-124 | [13 empty] | On Time
ACT-125 | [13 empty] | On Time
ACT-126 | [13 empty] | On Time
ACT-127 | [13 empty] | On Time
ACT-128 | [13 empty] | On Time
ACT-129 | [13 empty] | On Time
ACT-130 | [13 empty] | On Time
ACT-131 | [13 empty] | On Time
ACT-132 | [13 empty] | On Time
ACT-133 | [13 empty] | On Time
ACT-134 | [13 empty] | On Time
ACT-135 | [13 empty] | On Time
ACT-136 | [13 empty] | On Time
ACT-137 | [13 empty] | On Time
ACT-138 | [13 empty] | On Time
ACT-139 | [13 empty] | On Time
ACT-140 | [13 empty] | On Time
ACT-141 | [13 empty] | On Time
ACT-142 | [13 empty] | On Time
ACT-143 | [13 empty] | On Time
ACT-144 | [13 empty] | On Time
ACT-145 | [13 empty] | On Time
ACT-146 | [13 empty] | On Time
ACT-147 | [13 empty] | On Time
ACT-148 | [13 empty] | On Time
ACT-149 | [13 empty] | On Time
ACT-150 | [13 empty] | On Time
ACT-151 | [13 empty] | On Time
ACT-152 | [13 empty] | On Time
ACT-153 | [13 empty] | On Time
ACT-154 | [13 empty] | On Time
ACT-155 | [13 empty] | On Time
ACT-156 | [13 empty] | On Time
ACT-157 | [13 empty] | On Time
ACT-158 | [13 empty] | On Time
ACT-159 | [13 empty] | On Time
ACT-160 | [13 empty] | On Time
ACT-161 | [13 empty] | On Time
ACT-162 | [13 empty] | On Time
ACT-163 | [13 empty] | On Time
ACT-164 | [13 empty] | On Time
ACT-165 | [13 empty] | On Time
ACT-166 | [13 empty] | On Time
ACT-167 | [13 empty] | On Time
ACT-168 | [13 empty] | On Time
ACT-169 | [13 empty] | On Time
ACT-170 | [13 empty] | On Time
ACT-171 | [13 empty] | On Time
ACT-172 | [13 empty] | On Time
ACT-173 | [13 empty] | On Time
ACT-174 | [13 empty] | On Time
ACT-175 | [13 empty] | On Time
ACT-176 | [13 empty] | On Time
ACT-177 | [13 empty] | On Time
ACT-178 | [13 empty] | On Time
ACT-179 | [13 empty] | On Time
ACT-180 | [13 empty] | On Time
ACT-181 | [13 empty] | On Time
ACT-182 | [13 empty] | On Time
ACT-183 | [13 empty] | On Time
ACT-184 | [13 empty] | On Time
ACT-185 | [13 empty] | On Time
ACT-186 | [13 empty] | On Time
ACT-187 | [13 empty] | On Time
ACT-188 | [13 empty] | On Time
ACT-189 | [13 empty] | On Time
ACT-190 | [13 empty] | On Time
ACT-191 | [13 empty] | On Time
ACT-192 | [13 empty] | On Time
ACT-193 | [13 empty] | On Time
ACT-194 | [13 empty] | On Time
ACT-195 | [13 empty] | On Time
ACT-196 | [13 empty] | On Time
ACT-197 | [13 empty] | On Time
ACT-198 | [13 empty] | On Time
ACT-199 | [13 empty] | On Time
ACT-200 | [13 empty] | On Time
Formulas:
Days Open = IF([Status]="Completed",IF(ISBLANK([Completed Date]),"",[Completed Date]-[Created Date]),IF(ISBLANK([Created Date]),"",TODAY()-[Created Date]))
Days Remaining = IF([Status]="Completed",0,IF(ISBLANK([Due Date]),"",[Due Date]-TODAY()))

## Audit & Compliance Log
AUDIT & COMPLIANCE LOG Record of all audits, assessments, and compliance reviews
Audit Summary
Audit Type | Total Audits | Open Findings | Closed Findings | Avg Time to Close | Compliance Rate
Internal Audit | 0
External Audit | 0
Self-Assessment | 0
Vendor Audit | 0
Regulatory Inspection | 0
TOTAL | 0 | 0 | 0 | #DIV/0! | #DIV/0!
AUDIT REGISTER
Audit ID | Audit Type | Audit Scope | Assessment Area | Auditor/Assessor | Audit Date | Audit Report Date | Total Findings | Critical Findings | High Findings | Medium Findings | Low Findings | Open Findings | Closed Findings | Compliance Score | Report Location | Follow-up Required | Follow-up Date | Status | Notes
AUD-001
AUD-002
AUD-003
AUD-004
AUD-005
AUD-006
AUD-007
AUD-008
AUD-009
AUD-010
AUD-011
AUD-012
AUD-013
AUD-014
AUD-015
AUD-016
AUD-017
AUD-018
AUD-019
AUD-020
AUD-021
AUD-022
AUD-023
AUD-024
AUD-025
AUD-026
AUD-027
AUD-028
AUD-029
AUD-030
AUD-031
AUD-032
AUD-033
AUD-034
AUD-035
AUD-036
AUD-037
AUD-038
AUD-039
AUD-040
AUD-041
AUD-042
AUD-043
AUD-044
AUD-045
AUD-046
AUD-047
AUD-048
AUD-049
AUD-050
AUD-051
AUD-052
AUD-053
AUD-054
AUD-055
AUD-056
AUD-057
AUD-058
AUD-059
AUD-060
AUD-061
AUD-062
AUD-063
AUD-064
AUD-065
AUD-066
AUD-067
AUD-068
AUD-069
AUD-070
AUD-071
AUD-072
AUD-073
AUD-074
AUD-075
AUD-076
AUD-077
AUD-078
AUD-079
AUD-080
AUD-081
AUD-082
AUD-083
AUD-084
AUD-085
AUD-086
AUD-087
AUD-088
AUD-089
AUD-090
AUD-091
AUD-092
AUD-093
AUD-094
AUD-095
AUD-096
AUD-097
AUD-098
AUD-099
AUD-100

## Approval Sign-Off
ASSESSMENT APPROVAL AND SIGN-OFF
Dashboard Summary
Assessment Document | ISMS-IMP-A.8.24.5 - Compliance Summary Dashboard
Assessment Period
Portfolio Compliance (Average) | 79.1%
Dashboard Status
ASSESSMENT COMPLETED BY
Name:
Role/Title:
Department:
Email:
Date:
REVIEWED BY (INFORMATION SECURITY OFFICER)
Name:
Date:
Review Notes:
APPROVED BY (CISO)
Name:
Date:
Approval Decision:
Conditions/Notes:
NEXT REVIEW DETAILS
Next Review Date:
Review Responsible:
Special Considerations: