## Instructions & Legend
ISMS-IMP-A.5.35-36.S3 - Findings and Remediation Management ISO/IEC 27001:2022 - Control A.5.35-36: Compliance & Review
Document Information
Document ID | ISMS-IMP-A.5.35-36.S3
Workbook Title | Findings and Remediation Management
Control Reference | ISO/IEC 27001:2022 - Control A.5.35-36: Compliance & Review
Version | 1.0
Assessment Date
Completed By
Organisation
Instructions
1. Complete Findings Register — log all compliance findings with severity, source, and date.
2. Complete Remediation Actions — assign owners, resources, and target dates to each finding.
3. Complete Root Cause Analysis — identify systemic causes to prevent recurrence.
4. Complete Verification Log — record evidence that each remediation action is completed.
5. Review Trend Analysis — identify recurring finding types requiring systemic improvement.
6. Maintain Evidence Records with finding reports and remediation evidence.
7. Obtain final approval and sign-off in the Approval Sign-Off sheet.
Status Legend
Symbol | Status | Description
✓ | Compliant / Complete | Requirement fully met
⚠ | Partial / In Progress | Partially met or in progress
✗ | Non-Compliant / Not Started | Requirement not met
— | Not Applicable | Not applicable to this assessment

## Findings Register
CONSOLIDATED FINDINGS REGISTER
Consolidated register of all findings from independent reviews and compliance assessments — track severity, owner, and status through to closure.
Finding ID | Source | Source Ref | Finding Date | Finding Type | Severity | Control Reference | Finding Description | Root Cause | Recommendation | Owner | Target Date | Status | Days Open
FND-001 | Independent Review | REV-2026-001 | 15.03.2026 | Non-Conformity | Major | A.5.15, A.8.5 | MFA not enforced for privileged accounts in cloud environment | Policy gap — MFA policy not updated following cloud migration | Enforce MFA for all admin accounts in Azure AD within 30 days | IT Operations Manager | 14.04.2026 | In Progress
Formulas:
Days Open = IF(AND([Finding Date]<>"",[Status]<>"Closed"),TODAY()-[Finding Date],"")

## Remediation Actions
REMEDIATION ACTION TRACKER
Track corrective and preventive actions arising from findings — assign action type, owner, target dates, and track completion through verification.
Action ID | Finding Ref | Action Description | Action Type | Owner | Start Date | Target Date | Actual Date | Status | % Complete | Verification Method | Notes
ACT-001 | FND-001 | Enable MFA for all privileged accounts in Azure AD | Corrective Action | IT Operations Manager | 16.03.2026 | 14.04.2026 |  | In Progress | 40% | System check — Azure AD MFA report | Phase 1 complete: admin accounts done; user accounts in progress

## Root Cause Analysis
ROOT CAUSE ANALYSIS
Document root cause analysis for significant findings — identify whether issues are systemic and define preventive actions to avoid recurrence.
RCA ID | Finding Ref | Problem Statement | Analysis Method | Root Cause Category | Root Cause Description | Contributing Factors | Systemic Issue | Preventive Actions | Analyst | Analysis Date
RCA-001 | FND-001 | MFA not enforced for privileged accounts following cloud migration | 5 Whys | Process | MFA policy was not updated when infrastructure migrated to Azure — process gap in change management | Lack of IS review gate in cloud migration project | Yes | Add IS review gate to all infrastructure change projects | CISO | 18.03.2026

## Verification Log
VERIFICATION LOG
Verify that remediation actions are effective — document verification method, evidence reviewed, outcome, and closure recommendation for each finding.
Verification ID | Finding Ref | Action Ref | Verification Date | Verifier | Verification Method | Evidence Reviewed | Verification Result | Closure Recommendation | Follow Up Required | Notes
VER-001 | FND-001 | ACT-001 | 20.04.2026 | CISO | System Check | Azure AD MFA enforcement report — all admins | Effective | Close | No | MFA confirmed active for all 45 privileged accounts — finding closed

## Trend Analysis
FINDINGS TREND ANALYSIS
Track findings volume and closure rates across review periods — monitor trends to identify systemic issues and measure improvement over time.
Period | Major NCs | Minor NCs | Observations | Total Findings | Closed This Period | Open at Period End | Avg Days to Close | Repeat Findings | Notes
Q1 2026 | 2 | 5 | 8 |  | 10 | 12 | 18 | 1 | Post-certification audit period
Q2 2026
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
Q1 2028

## Evidence Register
EVIDENCE REGISTER
Store references to all audit evidence collected during independent reviews and compliance assessments — maintain location, custodian, and retention details.
Evidence ID | Evidence Type | Description | Related Finding | Collection Date | Location | Collected By | Retention Until
EV-001 | Finding Report | Independent review report — MFA non-conformity (FND-001) | FND-001 | 15.03.2026 | /SharePoint/ISMS/Reviews/2026/Q1/FND-001-Report.pdf | CISO | 15.03.2029

## Summary Dashboard
FINDINGS AND REMEDIATION MANAGEMENT — SUMMARY DASHBOARD
ISO/IEC 27001:2022 ¦ Controls A.5.35-36: Independent Review and Compliance
TABLE 1: COMPLIANCE STATUS OVERVIEW
Assessment Area | Total Items | Compliant | Partial | Non-Compliant | N/A | Compliance %
Findings Management
Remediation Actions
Root Cause Analysis |  |  | 0 |  | 0
Effectiveness Verification |  |  |  |  | 0
TOTAL
TABLE 2: KEY METRICS
Metric | Value
Total Findings Registered
Major Non-Conformities
Minor Non-Conformities
Observations
Open Findings
Findings from Independent Reviews
Findings from Compliance Assessment
Total Remediation Actions
Actions Completed
Actions In Progress
Actions Not Started
Corrective Actions
Systemic Issues Identified (RCA)
Process-Related Root Causes
People-Related Root Causes
Technology-Related Root Causes
Total Verifications
Effective Verifications
Not Effective Verifications
Re-Work Required
TABLE 3: CRITICAL FINDINGS REQUIRING IMMEDIATE ATTENTION
Category | Finding | Count | Severity | Action Required
Findings Management | Major NCs open |  | Critical | Immediate escalation
Findings Management | All open findings |  | High | Assign remediation owner
Findings Management | Findings pending verification >30 days |  | High | Complete verification
Remediation | Actions not started |  | High | Start immediately
Remediation | Actions on hold |  | Medium | Review blockers
Root Cause Analysis | Systemic issues identified |  | High | Review prevention programme
Effectiveness | Verifications failed (Not Effective) |  | Critical | Re-work remediation
Effectiveness | Re-work required items |  | High | Rework action plan

## Approval Sign-Off
ASSESSMENT APPROVAL AND SIGN-OFF
ISO/IEC 27001:2022 - Control A.5.35-36: Compliance & Review
ASSESSMENT SUMMARY
Document: | ISMS-IMP-A.5.35-36.S3 - Findings and Remediation Management
Assessment Period:
Overall Compliance Rating:
Assessment Status:
Assessed By:
COMPLETED BY (ASSESSOR)
Name:
Title:
Date:
Signature:
Comments:
REVIEWED BY (INFORMATION SECURITY OFFICER)
Name:
Title:
Date:
Signature:
Comments:
APPROVED BY (CISO)
Name:
Title:
Date:
Signature:
Comments:
FINAL DECISION:
NEXT REVIEW DETAILS
Next Review Date:
Review Responsible:
Special Considerations: