## Instructions & Legend
ISMS-IMP-A.5.8.3 - Project Portfolio ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management
Document Information
Document ID | ISMS-IMP-A.5.8.3
Workbook Title | Project Portfolio
Control Reference | ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management
Version | 1.0
Assessment Date
Completed By
Organisation
Instructions
1. Extract data from A.5.8.1 workbooks — populate Project Data sheet.
2. OR: Use consolidate_a58_dashboard.py for automated extraction.
3. Review Executive Summary for portfolio health status.
4. Review Gap Analysis for common security gaps.
5. Track trends quarter-over-quarter in Trend Analysis sheet.
6. Update quarterly or after major project milestones.
Status Legend
Symbol | Status | Description
✓ | Compliant / Complete | Requirement fully met
⚠ | Partial / In Progress | Partially met or in progress
✗ | Non-Compliant / Not Started | Requirement not met
— | Not Applicable | Not applicable to this assessment

## Project Data
PROJECT DATA TABLE
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Consolidated project security data from A.5.8.1 lifecycle assessments
Project Name | Classification | PM | Business Owner | Phase | Compliance % | Initiation % | Planning % | Execution % | Monitoring % | Closure % | Critical Gaps | High Findings | Deploy Date | Last Assessment | Notes
Customer Portal v2.0 | High | Jane Smith | Commercial Director | Execution | 72% | 100% | 88% | 72% |  |  | 2 | 5 |  |  | On track — security testing in progress

## Summary Dashboard
Project Portfolio — SUMMARY DASHBOARD
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management
COMPLIANCE ASSESSMENT SUMMARY
Assessment Area | Questions Answered | No Gap | Gap Identified | N/A | Target | Compliance %
Portfolio Compliance |  |  |  | 0 | 80%
Regulatory Compliance |  |  |  | 0 | 90%
TOTAL |  |  |  |  | —
PORTFOLIO ANALYTICS
Metric | Value | Target
Total Projects |  | ≥1
High Risk Projects |  | —
Portfolio Avg Compliance (%) |  | ≥70%
Projects ≥85% Compliant |  | —
Projects <70% At Risk |  | 0
Total Critical Gaps |  | 0
CRITICAL FINDINGS
Critical Finding | Status | Severity
Portfolio Compliance <70% |  | Critical
Regulatory Compliance <80% |  | Critical
Overall compliance <70% |  | Critical
High-risk projects >5 |  | High
Projects at-risk >3 (<70%) |  | Critical

## Project Status
PROJECT STATUS
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Per-project security compliance status linked from Project Data
Project | Classification | Phase | Compliance % | Critical Gaps | Status | Owner | Notes

## Gap Analysis
GAP ANALYSIS
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Common security gaps identified across the project portfolio
Gap Category | Description | Frequency | Impact | Recommended Action
Access Control | MFA not consistently implemented across high-risk projects | 8 | High | Mandate MFA for all Tier 1/2 system projects via updated security gate criteria

## Trend Analysis
TREND ANALYSIS
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Quarter-over-quarter security compliance trends across the portfolio
Quarter | Total Projects | Avg Compliance % | High Risk Avg | Medium Risk Avg | Low Risk Avg
Q1-2026 | 8 | 71% | 65% | 74% | 82%

## Risk Prioritisation
RISK PRIORITISATION MATRIX
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Priority ranking of projects requiring security remediation action
Priority | Project Name | Classification | Compliance % | Critical Gaps | Action Required
P1 | Customer Portal v2.0 | High | 52% | 3 | Immediate: Schedule security gate review — 3 critical gaps open

## Lessons Learned
LESSONS LEARNED SYNTHESIS
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Cross-project insights and recommendations for future projects
Project | Lesson Learned | Category | Recommendation
Customer Portal v2.0 | Security requirements defined late — caused 3-week delay during execution phase | Requirements Definition | Mandate security gate at project initiation: complete requirements register before planning phase begins

## Regulatory Compliance
REGULATORY COMPLIANCE VIEW
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Compliance status by regulation across the portfolio
Regulation | Applicable Projects | Compliance Rate | Gaps | Status
GDPR
nDSG (Swiss DPA)
PCI DSS v4.0.1
HIPAA
ISO 27001
SOC 2

## Resources & Budget
RESOURCES & BUDGET ANALYSIS
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management — Security budget allocation and resource utilisation per project
Project | Security Budget (CHF) | Actual Spend (CHF) | % of Total Budget | Resource FTE
Customer Portal v2.0 | 45000 | 32500 | 8% | 1.5

## Charts
VISUALISATION PLACEHOLDERS
CHART PLACEHOLDERS
Create charts in Excel based on data from other sheets:
1. Portfolio Compliance Score - Gauge chart
2. Projects by Risk Classification - Pie chart
3. Compliance Distribution - Bar chart
4. Trend Analysis - Line chart (QoQ)
5. Gap Analysis - Pareto chart
6. Budget Allocation - Stacked bar chart

## Approval Sign-Off
ASSESSMENT APPROVAL AND SIGN-OFF
ISO/IEC 27001:2022 - Control A.5.8: Information Security in Project Management
ASSESSMENT REVIEW AND APPROVAL
Role / Function | Name | Signature / Initials | Date (DD.MM.YYYY) | Comments
Lead Assessor / Author
IT Security Manager
Reviewer (Technical / Compliance)
CISO / Final Approver
FINAL DECISION:
NEXT REVIEW
Next Review Date (DD.MM.YYYY)
Review Owner