## Executive_Dashboard
REGULATORY COMPLIANCE DASHBOARD
Last Updated: 08.02.2026 12:25
KEY PERFORMANCE INDICATORS
Total Regulations Tracked |  | 🟢 15 | Tier 1 (Mandatory) |  | 🔴 5
Tier 2 (Conditional) |  | 🟡 3 | Total Requirements |  | 127
Requirements Implemented |  | 🟢 89 | Implementation Progress |  | 🟡 70%
Control Gaps Identified |  | ⚠ 12 | Evidence Items Collected |  | 156
Evidence Audit Ready |  | 🟢 142 | Audit Readiness |  | 🟢 91%
⚠ CRITICAL ALERTS
🔴 URGENT | TLS Certificate Expired |  |  | 30 days overdue |  | Security Engineer
🔴 HIGH | FDPIC Notification Procedure Missing |  |  | Tier 1 requirement |  | Incident Response Lead
🟡 MEDIUM | 3 Requirements approaching deadline |  |  | Within 30 days |  | CISO
📅 UPCOMING ACTIONS (Next 30 Days)
2025-01-15 | Q1 Risk Assessment |  |  | REG-ISO27001-6.1-001 |  | CISO
2025-01-20 | Database Encryption Verification |  |  | REG-FADP-7-001 |  | Database Admin
2025-02-01 | Vulnerability Scan Q1 2025 |  |  | REG-NIS2-21-001 |  | Security Ops

## Regulatory_Status
REGULATORY COMPLIANCE STATUS
Reg ID | Regulation | Tier | Status | Requirements | Implemented | Progress | Gaps | Next Review
REG-EU-001 | GDPR | Tier 1 | ✅ Compliant | 32 | 28 | 88% | 4 | 2025-06-01
REG-INT-001 | ISO 27001:2022 | Tier 1 | ⏳ In Progress | 93 | 65 | 70% | 28 | 2025-12-31
REG-CH-001 | Swiss FADP | Tier 1 | ⚠ Partial | 15 | 10 | 67% | 5 | 2025-09-01
REG-EU-002 | NIS2 | Tier 2 | 🔍 Monitoring | 8 | 0 | 0% | 8 | 2025-04-01
REG-VOL-001 | NIST CSF 2.0 | Tier 3 | ⏳ In Progress | 12 | 8 | 67% | 4 | 2026-06-30

## Requirements_Progress
REQUIREMENTS IMPLEMENTATION PROGRESS
BY CATEGORY
Category | Total Reqs | Implemented | Progress | Gaps
Technical | 45 | 32 | 71% | 13
Organizational | 38 | 30 | 79% | 8
Reporting | 18 | 12 | 67% | 6
Operational | 26 | 15 | 58% | 11
BY PRIORITY
Category | Total Reqs | Implemented | Progress | Gaps
🔴 High Priority | 52 | 42 | 81% | 10
🟡 Medium Priority | 48 | 32 | 67% | 16
🟢 Low Priority | 27 | 15 | 56% | 12
BY TIER
Category | Total Reqs | Implemented | Progress | Gaps
Tier 1 (Mandatory) | 95 | 75 | 79% | 20
Tier 2 (Conditional) | 20 | 8 | 40% | 12
Tier 3 (Informational) | 12 | 6 | 50% | 6

## Control_Coverage
ISO 27001 CONTROL COVERAGE
CONTROL IMPLEMENTATION STATUS
Section | Total Controls | Implemented | In Progress | Not Started | % Complete
5 - Organizational | 37 | 28 | 7 | 2 | 76%
6 - People | 8 | 6 | 2 | 0 | 75%
7 - Physical | 14 | 10 | 3 | 1 | 71%
8 - Technological | 34 | 21 | 10 | 3 | 62%
TOTAL | 93 | 65 | 22 | 6 | 70%

## Evidence_Health
EVIDENCE COLLECTION & HEALTH
EVIDENCE STATUS SUMMARY
Total Evidence Items | 156
{CHECK} Verified & Current | 132 (85%)
⏳ Pending Verification | 12 (8%)
{XMARK} Expired / Outdated | 8 (5%)
❓ Missing / Not Collected | 4 (3%)
Audit Ready Status
{CHECK} Audit Ready | 142 (91%)
{WARNING} Needs Update | 10 (6%)
{XMARK} Not Audit Ready | 4 (3%)

## Action_Items
COMPLIANCE ACTION ITEMS
Priority | Action | Requirement | Due Date | Owner | Status
🔴 URGENT | Renew TLS Certificate | REG-GDPR-32-001 | 2025-01-12 | Security Engineer | ❌ Overdue
🔴 HIGH | Create FDPIC Notification Procedure | REG-FADP-24-001 | 2025-01-31 | Incident Response Lead | ⏳ In Progress
🟡 MEDIUM | Update Breach Notification Procedure | REG-GDPR-33-001 | 2025-02-15 | Compliance Officer | ⏳ In Progress
🟡 MEDIUM | Verify Database Encryption | REG-FADP-7-001 | 2025-01-20 | Database Admin | ➖ Not Started
🟢 LOW | Annual ISMS Policy Review | REG-ISO27001-5.1-001 | 2025-12-15 | ISMS Manager | ➖ Not Started

## Instructions
COMPLIANCE DASHBOARD - USER GUIDE
PURPOSE:
Executive overview of regulatory compliance status across all regulations, requirements, controls, and evidence.
DASHBOARD SHEETS:
1. Executive Dashboard - High-level KPIs and critical alerts
2. Regulatory Status - Compliance status per regulation
3. Requirements Progress - Implementation progress by category/priority/tier
4. Control Coverage - ISO 27001 control implementation status
5. Evidence Health - Evidence collection and verification status
6. Action Items - Prioritized compliance actions
DATA SOURCES:
This dashboard consolidates data from:
• Workbook 1: Regulatory Inventory
• Workbook 2: Applicability Matrix
• Workbook 3: Requirements Register
• Workbook 4: Control Mapping Matrix
• Workbook 5: Evidence Register
REFRESH FREQUENCY:
Update this dashboard: Weekly (or after significant changes)