## Instructions & Legend
ISMS-IMP-A.5.8.1 - Project Lifecycle Security Assessment\nISO/IEC 27001:2022 Control A.5.8
DOCUMENT CONTROL
Document ID: | ISMS-IMP-A.5.8.1
Version: | 2.0
Control Reference: | ISO/IEC 27001:2022 Control A.5.8
Purpose: | Assess security integration across project lifecycle (6 phases)

## 2. Project Classification
PHASE 0: PROJECT CLASSIFICATION\nDetermine Risk Level (High/Medium/Low)
Project Name:
Project Manager:
CLASSIFICATION WORKSHOP (30-60 minutes)
1. Gather stakeholders: PM, Security, Business Owner, Technical Lead (5 min)
2. Review each factor below and score High/Medium/Low (20-30 min)
3. Discuss edge cases and document rationale (10-15 min)
4. Confirm final classification and next steps (5 min)
CLASSIFICATION DECISION MATRIX (6 Factors):
Factor | High (3 pts) | Medium (2 pts) | Low (1 pt) | Score | Rationale
Data Sensitivity | Restricted/Special Category PII | Confidential/Internal PII | Public/Non-sensitive
System Criticality | Tier 1 (RTO <4hr) | Tier 2 (RTO 4-24hr) | Tier 3+ (RTO >24hr)
Regulatory Scope | Multiple regulations (GDPR+PCI+etc) | Single major regulation | General compliance only
External Exposure | Internet-facing, customer data | Partner/B2B access | Internal only
Technical Complexity | New technology, high integration | Moderate complexity | Standard/proven stack
Third-Party Involvement | Critical outsourced development | Vendor components | Internal development
TOTAL SCORE:
CALCULATED RISK LEVEL:
(High: 15-18 pts ¦ Medium: 10-14 pts ¦ Low: 6-9 pts)
COMMON CLASSIFICATION SCENARIOS (Reference Examples):
Scenario Description | Typical Classification | Key Factors
Customer-facing web portal with payment processing | High | External exposure + PCI DSS v4.0.1 + customer PII
Internal HR system with employee data | Medium | Internal PII but limited exposure
Marketing website refresh (static content) | Low | Public data, no integration
Cloud migration of core ERP system | High | Critical system + complexity + third-party
Mobile app for field service technicians | Medium | Internal users but external network
Data analytics dashboard (aggregated metrics) | Low | No PII, internal only
Third-party SaaS integration (CRM) | Medium | Vendor involvement + customer data subset
Legacy system decommissioning | Medium | Data retention + secure disposal needs

## 3. Initiation Phase
PHASE 1: INITIATION
Activity | Status | Completion Date | Evidence Link | Notes
Identify security stakeholders and establish communication plan
Conduct initial risk assessment and document key risks
Define security requirements baseline
Allocate security budget and resources
Document security responsibilities in project charter
Obtain Phase 1 gate approval from security team

## 4. Planning Phase
PHASE 2: PLANNING
Activity | Status | Completion Date | Evidence Link | Notes
Document detailed security requirements (link to A.5.8.2 Register)
Conduct threat modeling and document threat scenarios
Develop security test plan and define test cases
Complete Data Protection Impact Assessment (DPIA) if required
Conduct vendor security assessment if third-party components
Define security monitoring and logging requirements
Establish incident response procedures
Obtain Phase 2 gate approval from security team

## 5. Execution Phase
PHASE 3: EXECUTION
Activity | Status | Completion Date | Evidence Link | Notes
Execute security testing per test plan (SAST, DAST, etc.)
Conduct penetration testing and document findings
Complete vulnerability scans and remediate critical/high findings
Review and approve security architecture/design
Verify secure coding practices and code review completion
Test security controls and verify implementation
Document security configurations and hardening
Update threat model with implementation changes
Obtain Phase 3 gate approval from security team

## 6. Monitoring Phase
PHASE 4: MONITORING
Activity | Status | Completion Date | Evidence Link | Notes
Monitor ongoing compliance with security requirements
Review and update risk assessments for changes
Assess security impact of change requests
Track security metrics and KPIs
Obtain Phase 4 gate approval for major milestones

## 7. Closure Phase
PHASE 5: CLOSURE
Activity | Status | Completion Date | Evidence Link | Notes
Complete security handover documentation
Verify all security testing complete and passed
Document residual risks and obtain risk acceptance
Conduct lessons learned session with security team
Archive security documentation and evidence
Obtain final security sign-off for production deployment

## 8. Compliance Dashboard
COMPLIANCE DASHBOARD\nAutomated Phase Completion Scores
PROJECT INFORMATION
Project Name:
Risk Classification:
Assessment Date:
PHASE COMPLETION SCORES
Phase | Completion %
Initiation
Planning
Execution
Monitoring
Closure
OVERALL COMPLIANCE:

## 9. Evidence Register
EVIDENCE REGISTER\nAudit Evidence Tracking
Evidence ID | Phase | Description | Location/Path | Date Collected | Status

## 10. Sign-Off
SIGN-OFF & APPROVAL\nMulti-Stakeholder Approval Workflow
ASSESSMENT SUMMARY
Project Name:
Overall Compliance:
APPROVALS
Role | Name | Signature | Date | Decision
Project Manager
Security Team
Final Approver